## 000-A-PPN-60002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | Robert.Kawitzki | Text unreadable. Text height shall be as per project standards. Split drawing if required
2 | Callout |  | Robert.Kawitzki | Use correct font for a matchline
3 | Callout |  | Robert.Kawitzki | Drawing form shall be filled out correctly
4 | Callout |  | Robert.Kawitzki | Text height to project standards - typical comment
5 | Callout |  | Robert.Kawitzki | Work areas shall be located with eastings and northings - typical comment
6 | Callout |  | Robert.Kawitzki | Match line continuation missing
7 | Callout |  | Robert.Kawitzki | Main roads shall be located with northings and eastings - typical comment
8 | Typewritten Text |  | Mohamed Ayyash | Slop rerun
9 | Typewritten Text |  | Mohamed Ayyash | does not
10 | Typewritten Text |  | Mohamed Ayyash | exist any more (demolished many years ago)
11 | Arrow |  | Mohamed Ayyash
12 | Arrow |  | Mohamed Ayyash
13 | Typewritten Text |  | Mohamed Ayyash | You can say old control room or Work station
14 | Line |  | Mohamed Ayyash
15 | Microsoft Word - Code 3 With Comments |  | Adel