## 000-A-PRI-50012-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Microsoft Word - Code 3 With Comments.docx | 1 | Harshad.K.Patel
| Cloud | 1 | Mahdi Ali
| Arrow | 3 | Mohamed Ayyash
2 | Text Box | 3 | Mahdi Ali | Definition of Supplier is missing.
3 | Call-out | 3 | Ali Abbas | Control/ESD Valves actual sizes
4 | Text Box | 4 | Mahdi Ali | If the Supplier provided high level of details, then Contractor shall use it.
5 | Text Box | 4 | Mahdi Ali | 3D
6 | Callout | 4 | Robert.Kawitzki | Including motor connection boxes
7 | Text Box | 4 | Robert.Kawitzki | Lighting
8 | Callout | 4 | Robert.Kawitzki | including mounting points of skids
| Text Box | 4 | Mahdi Ali
| Strikethrough | 4 | Mahdi Ali
9 | Text Box | 4 | Mahdi Ali | Equipment shall be included in the 30% as per section 8.9 of BMPS-A8
10 | Text Box | 5 | Robert.Kawitzki | Software used shall comply with BMPS-A8 unless approved by client. Packages shall be modeled with the same degree of detail of the rest of the plant as per BMPS-A8 9.3.1.3
11 | Text Box | 5 | Mahdi Ali | This document fails to include how JV will integrate the final Suppliers 3D model into the integrated 3D model. JV 3D model shall be in Intergraph's S3D format inclusive of all content. Bapco's intent is to maintain the 3D model for its entire plant life cycle and shall be able to modify the content of the 3D model without the use of the source (native) tools used to generate the 3D model. The 3D model from the Supplier must be editable in S3D format. The Supplier 3D model shall be dimensionally measurable and can be checked for soft/hard clash detections. All the equipment tags shall be as per Bapco naming conventions.
| Arrow | 6 | Mohamed Ayyash
| Arrow | 6 | Mohamed Ayyash
12 | Callout | 6 | Mohamed Ayyash | don't use justify for better appearance
13 | Text Box | 7 | Jeung.Kim
14 | Text Box | 7 | Robert.Kawitzki | Irregardless of the source extension, deliverable shall be readable and able to be modified with the project specified software
| Arrow | 7 | Jeung.Kim