## 000-A-PRO-50002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | Jeung.Kim | suggest to add document title in the header for easy identification.
2 | Text Box |  | Harshad.K.Patel | Please add below information to Paragraph section 11 (Emails) and update the procedure accordingly. Coordination Protocol using Mail Boxes for Bapco: Two Project Mail Boxes will be used by Bapco as an official communication tool to electronically transmit Letters, MOMs, Reports and technical information between TTSJV and Bapco. 1. Mail Box (EN0815@BapcoBMP.com) will be used to receive and send TRANSMITTALS only between TTSJV and Bapco 2. Mail Box (EN0815-PM@BapcoBMP.com) will be used for exchange of TECHNICAL INFORMATION (transfer of technical information without Transmittals e.g. drawing requests, confirmation of technical issues, etc.) between TTSJV and Bapco; this mail box can be classified as one which is to be used for NON-TRANSMITTALS. Only emails duly transmitted by TTSJV to the two mail boxes mentioned above shall be considered as official communication. On Bapco side, only those emails transmitted through mail box EN0815@BapcoBMP.com or EN0815-PM@BapcoBMP.com shall be considered as official communication. Such emails shall only be issued with the authorization of BMP Project Director or his dully appointed delegate(s). All such emails, when originating from Bapco or TTSJV, shall be numbered in accordance with the documentation procedure. It should include the origin of the email (e.g. Directorate, ROC, MOC, SOC). Official responses from the parties mentioned above shall be provided as a RE or FW to the original email to maintain subject continuity for future references. Emails written from/to addresses rather than the Project official ones listed shall be used only for informal communications between Bapco & TTSJV counterparts.
3 | Stamp |  | Harshad.K.Patel
4 | Callout |  | Jeung.Kim | leads
5 | Highlight |  | Stephen.Jackson
6 | Pen |  | Stephen.Jackson | .
7 | Note |  | Stephen.Jackson | All offices ill be available to Owner 7 days a week plus a minimum 2 hours either side of Contractors core working hours
8 | Call-out |  | Ranjit | Approaching Project Director for international calls is inefficient. We should be able to call through project code.
9 | Call-out |  | Ranjit | Not complete. Provide
10 | Cloud |  | Ranjit
11 | Call-out |  | Ranjit | Update for all OCs
12 | Call-out |  | Ranjit | Project Director
13 | Cloud |  | Ranjit
14 | Call-out |  | Ranjit | update for other OCs
15 | Callout |  | Jeung.Kim | SECL needs to confirm it as there is missing such as May day,
16 | Text Box |  | Mahdi Ali | If the Official letters are considered for the final handover then it must have BAPCO number.
17 | Text Box |  | Mahdi Ali | If the Technical Memos are considered for the final handover then it must have BAPCO number.
18 | Callout |  | Jeung.Kim | Please provide this scope split in between OC's.
19 | Note |  | Nalini Mohan | Harshad, Bapco OC team is lead by PM and not by PD. Discuss this aspect internally.
20 | Call-out |  | Nalini Mohan | Please explain what kind of communication can be covered under this as letters, TMs, Transmittals are already covered between JV and Bapco Project Directorate
21 | Call-out |  | Nalini Mohan | How will RFIs (Request for Information) be handled? Will relevant OC directly communicate with Bapco OC team or will it be through Directorate?
22 | Cloud |  | Ranjit
23 | Call-out |  | Ranjit | update
24 | Callout |  | Harshad.K.Patel | Manager
25 | Text Box |  | Mahdi Ali | If the MOM is considered for the final handover then it must have BAPCO number with MOM document type.
26 | Text Box |  | Jeung.Kim | There is no procedure stated here for each Operation Center. Can we understand no official email email communication is allowed to each OC?
27 | Text Box |  | Mahdi Ali | Bapco Document number shall be included
28 | Call-out |  | Ravi Kumar | BMP or BMD?
29 | Callout |  | Jeung.Kim | and?
30 | Highlight |  | Stephen.Jackson
31 | Note |  | Stephen.Jackson | Should be Project Director..change throughout Document
32 | Call-out |  | MAK | Change to the new email address: Savas@BapcoBMP.com
33 | Call-out |  | Ali Hasan | #2, #3 BAGRU instead of #1, #2 BAGRU
34 | Call-out |  | Ali Hasan | 4A CDU maxmium operating capacity is 105 MBPD, not 85 MBPD
35 | Call-out |  | Ali Hasan | #2, #3 BAGRU instead of #1, #2 BAGRU
36 | Call-out |  | Ali Hasan | change to TGTU
37 | Call-out |  | Hasan Al Noaimi
38 | Highlight |  | Hasan Al Noaimi
39 | Highlight |  | Hasan Al Noaimi
40 | Highlight |  | Hasan Al Noaimi
41 | Highlight |  | Hasan Al Noaimi
42 | Highlight |  | Hasan Al Noaimi
43 | Highlight |  | Hasan Al Noaimi
44 | Highlight |  | Hasan Al Noaimi
45 | Highlight |  | Hasan Al Noaimi
46 | Highlight |  | Hasan Al Noaimi
47 | Highlight |  | Hasan Al Noaimi
48 | Highlight |  | Hasan Al Noaimi
49 | Call-out |  | Hasan Al Noaimi | 1BAGRU at LSDP
50 | Call-out |  | Hasan Al Noaimi
51 | Call-out |  | Hasan Al Noaimi
52 | Call-out |  | Hasan Al Noaimi | No 3H2Plant and No4 H2Plant
53 | Call-out |  | Hasan Al Noaimi | Hydrogen Recovery Unit 1HRU
54 | Call-out |  | Hasan Al Noaimi | 60MBPD 67percent conversion but normally 53 MBPD to meet LBOP specification.
55 | Pen |  | Hasan Al Noaimi
56 | Pen |  | Hasan Al Noaimi
57 | Call-out |  | Hasan Al Noaimi | purity 94 percent
58 | Call-out |  | Hasan Al Noaimi | purity 99.9 percent
59 | Call-out |  | Hasan Al Noaimi
60 | Highlight |  | Hasan Al Noaimi
61 | Highlight |  | Hasan Al Noaimi
62 | Highlight |  | Hasan Al Noaimi
63 | Highlight |  | Hasan Al Noaimi
64 | Call-out |  | Hasan Al Noaimi
65 | PolyLine |  | Hasan Al Noaimi
66 | PolyLine |  | Hasan Al Noaimi | No 1 Hydrocracking Unit
67 | PolyLine |  | Hasan Al Noaimi
68 | Call-out |  | Hasan Al Noaimi
69 | Call-out |  | Ranjit | 38 MMSCFD
70 | Call-out |  | Ranjit | Provide capacity in MMSCFD of Hydrogen product
71 | Call-out |  | Ali Hasan | The maximum operating capacity of the Sulphur Plant is 790 MTPD: 1SRU: 170 MT/day 2SRU: 170 MT/day 3SRU: 225 MT/day 4SRU: 225 MT/day