## 000-A-PRO-50018-001-RA-bb comme
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | scott.hillman | There is no mention of a number of key Engineering Management requirements, including: - Squad Check/Inter-discipline review Procedure - KDCN Procedure - QA/QC plans While they may be part of separate documents, they are key requirements for Engineering Management, particularly where execution offices are split. High level requirements, at least, should be described here.
2 | Text Box |  | Harshad.K.Patel | Engineering work-flow information (as requested and referenced in Negotiations Road Map, Part 1, Item 4 under Technical & Execution Issues) should be included in this plan.
3 | Text Box |  | Harshad.K.Patel | Please revise & re-submit Engineering Management Plan per comments indicated in this document
4 | Stamp |  | Harshad.K.Patel
5 | Text Box |  | Hasan Al Noaimi
6 | Text Box |  | Mahdi Ali | Title of the document shall be added
7 | Highlight |  | Jeung.Kim
8 | Cloud |  | Mahdi Ali
9 | Text Box |  | Mahdi Ali | Unit abbreviations to follow the BMPS-A8 Part B Appendix 1. This example shall be 1RHCU and not #1RHCU (Typ.)
10 | Arrow |  | Jeung.Kim
11 | Text Box |  | Jeung.Kim | This term is not so much clearly define the level of detail- please clearly state its level.- suggest to detail it in each discipline.
12 | Arrow |  | Jeung.Kim
13 | Text Box |  | Jeung.Kim | No dedicated interface Coordinator is assigned in the SOC.
14 | Call-out |  | Nalini Mohan | OCs should also have access to Licensor for direct discussions (telephonic) for clarifying any subject. Formal communication with regard to deliverable review or attending design reviews could be between JV Directorate and Licensor
15 | Callout |  | scott.hillman | Discussions between technical reps at the kick off meeting should not be considered as the final resolution, as they bypass the review process that was in place during the Bid Clarifications, and the formal MoC process post contract signing. Discussions at the Kick of should be minuted and any changes managed through the correct channels.
16 | Arrow |  | Jeung.Kim
17 | Text Box |  | Jeung.Kim | Add the role of standardization, Harmonization and Homogenization
18 | Arrow |  | Jeung.Kim
19 | Text Box |  | Jeung.Kim | that?
20 | Cloud |  | Mahdi Ali
21 | Call-out |  | Ravi Kumar | Definition of IBD and level/quality of documents issued for IBD needs to be discussed and agreed as discussed during KOM. The documents shall meet the min requirements stated along with issue of updated EDP
22 | Callout |  | scott.hillman | This doesn't relate to Engineering Management. Delete from this document.
23 | Callout |  | scott.hillman | This statement is incorrect. Page 22 of the WP3 Scope for work, included in the ITB clearly states that the contractor shall install 2No. 18" supply lines, one from ADP and one from RDP. More over reference is made to them u058 Design Basis and PFD. This is not a change/alternative/option from FEED. The work will be completed as part of standard Detailed Design Development.
24 | Cloud |  | Mahdi Ali
25 | Cloud |  | Mahdi Ali
26 | Cloud |  | Mahdi Ali
27 | Arrow |  | Julio.Aguilar
28 | Arrow |  | Julio.Aguilar
29 | Cloud |  | Julio.Aguilar
30 | Cloud |  | Mahdi Ali
31 | Text Box |  | Mahdi Ali | Using SEED files from FEED and conversion of databases is not acceptable.
32 | Squiggly |  | Mahdi Ali
33 | Text Box |  | Mahdi Ali | The seed files are currently in USE by other EPC contractors for smaller size projects. Moreover, the seed files have been tested and found functional. FInally, BAPCO experience with Intergraph response is found to be satisfactory
34 | Text Box |  | Mahdi Ali | Decision has already been made to use BAPCO seed files.
35 | Callout |  | scott.hillman | Management of the Client Comments register will be the responsibility of the EPC Contractor. IPMT may AT IT'S OWN DISCRETION choose to issue comments with an accompanying spreadsheet, but will not be required to do so. If no spreadsheet is included, the EPC Contractor shall undertake this task, with no impact to the IPMT.
36 | Callout |  | Harshad.K.Patel | In accordance with BMPS A7 requirements
37 | Text Box |  | Harshad.K.Patel
38 | Call-out |  | Nalini Mohan | qq
39 | Call-out |  | Nalini Mohan
40 | Call-out |  | Nalini Mohan | TTSJV should provide Deliverable List in accordance with CDRL and add specific items not covered under CDRL. Deletion of items from CDRL should be done on exceptional cases after due approval from the OWNER. Just "COMPARING" with CDRL and providing "STANDARD" list is not acceptable
41 | Call-out |  | Nalini Mohan | How will Technical Query for specific OC will be handled? Will OC generate the query directly to Bapco or direct it through JV?
42 | Call-out |  | Nalini Mohan | What is the mechansim that JV will use to segregate General and Specific comments?
43 | Callout |  | Harshad.K.Patel | All FEED design needs to be validated in addition to what is indicated in Item 2.
44 | Callout |  | Raj | Lesson's Learnt from all OCs is an important value addition on FEED work. This doc need to exactly describe how LLs from other OCs shall be implemented during EPC. Discuss LL register and at which stage LL will be incorporated.
45 | Callout |  | scott.hillman | Regardless of any optimization report and deep analysis that has been done, it should be noted that progressing procurement activities based on FEED deliverables is done at the EPC Contractors own risk.
46 | Call-out |  | Nalini Mohan | FEED data sheets are incomplete and not fit for procurement as is
47 | Callout |  | Julio.Aguilar | All FEED equipment process data sheets shall be revised and completed by EPC Contractor.
48 | Text Box |  | Mahdi Ali | I suggest that all 3D model procedures combined in one document.
49 | Text Box |  | Mahdi Ali | What about the 2D drawings and reports generated from the 3D model?
50 | Callout |  | scott.hillman | The OBE should not be referenced in the Engineering Management document. Engineering documentation will be prepared to support a Technical Change Request, in line with the project's MoC procedure. The OBE is part of the commercial discussions that follow.
51 | Text Box |  | Mahdi Ali | All tags in SPPID must be correlated with relevant tags in SPI, SPEL and S3D.
52 | Call-out |  | Nalini Mohan | Package item details that were received beyond IDD1 should undergo separate HAZOP.
53 | Call-out |  | Ravi Kumar | A full HAZOP is required per BMPS-A15 as indicated in ITB
54 | Call-out |  | Ravi Kumar | HAZOP 3 timing should be that some preliminary design information of packages should be available and included in the unit P&IDs
55 | Call-out |  | Hasan Al Noaimi
56 | Call-out |  | Hasan Al Noaimi
57 | Call-out |  | Ali Hasan | TTSJV shall be responsible to conduct detailed HAZOP 3 during the EPC phase. Please refer to Owner response to query T1576 during the Technical clarification in which Owner clarify the intent and the scope of HAZOP 3.
58 | Call-out |  | Ali Hasan | Please add the following: The SIL report shall also determine the frequency of testing of each SIF. Sebsequently, this data shall be reflected in the A&T procedures which needs to be developed in each concerned OC.
59 | Call-out |  | Nalini Mohan | Will noise study be conducted by JV directly or specialist Acoustic Consultant be hired?
60 | Text Box |  | rob.urban | It needs to be verified with the licensor CLG if piping fatigue analysis is required for systems in the RHCU in cyclical conditions (reactor loop, catalyst handling etc)
61 | Call-out |  | Nalini Mohan | Bapco will not develop steam trap types & configurations. It is JV's responsibility
62 | Call-out |  | Nalini Mohan
63 | Call-out |  | Nalini Mohan
64 | Callout |  | scott.hillman | Provide additional detail on what units are considered revamped. Where the revamps are extensive, 3D models should be developed.
65 | Callout |  | scott.hillman | Wharf and existing tank farms also.
66 | Call-out |  | Ali Hasan | Add new bullet: The 3D Model will also include the revamped units in the brown-field area, such as installation of the new train (Train C) in KMU.
67 | Call-out |  | Nalini Mohan
68 | Call-out |  | Nalini Mohan | If model reviews are conducted in Directorate then Bapco IPMT (30-40 members) from SOC and MOC have to travel to Rome. JV Directorate should send its specialists to SOC and MOC for these reviews to ensure uniformity.
69 | Callout |  | Julio.Aguilar | Ensure that all new utility units are modeled as well.
70 | Callout |  | scott.hillman | Change the wording of this. Communication was note "lately", the removal of the roads to the South of the refinery was part of the Bid Clarification phase, which included the requirement for the EPC Contractor to complete a transport/logistics plan.
71 | Callout |  | scott.hillman | This section to be reviewed based on the Option of a new CCB.
72 | Arrow |  | Jeung.Kim
73 | Text Box |  | Jeung.Kim | shall the ergonomic study report be issued for Client review?
74 | Arrow |  | Jeung.Kim
75 | Text Box |  | Jeung.Kim | suggested to include the level and more details how to achieve the standardization, harmonization and homogenization- typical for all disciplines
76 | Text Box |  | rob.urban | What about pulsation analysis of the connected piping system (compressor loop) for reciprocating compressors? This is not mentioned
77 | Cloud |  | Mahdi Ali
78 | Cloud |  | Mahdi Ali
79 | Cloud |  | Mahdi Ali
80 | Text Box |  | Mahdi Ali | All Electrical tags in SPEL must be correlated with relevant tags in SPPID, SPI and S3D.
81 | Arrow |  | Sankara
82 | Text Box |  | Sankara | Electricity
83 | Text Box |  | Sankara | Identify the data requirements and coordinate with EWA/ESBI early so that the information will be received in time.
84 | Arrow |  | Sankara
85 | Arrow |  | Sankara
86 | Text Box |  | Sankara | I&A
87 | Text Box |  | Mahdi Ali | All Instrument tags in SPI must be correlated with relevant tags in SPPID, SPEL and S3D.
88 | Call-out |  | Nalini Mohan
89 | Call-out |  | Nalini Mohan | Add: Reliability figures (MTBF), past performance data of the model being proposed
90 | Call-out |  | Nalini Mohan
91 | Call-out |  | Nalini Mohan | Add: h) Asset Information Data i) Priced spare parts list for 2 year operation.
92 | Text Box |  | Mahdi Ali | A QA/QC procedure shall be prepared for the As-built.
93 | Text Box |  | Jeung.Kim | suggested to add the detail scopes of each OC
94 | Rectangle |  | Jeung.Kim
95 | Callout |  | Raj | The Scope of Work for each Work Package is already covered in Vol 4, Vol 5 and Vol 6. EPC to make use of the content and prepare a more detailed scope of work
96 | Call-out |  | Ali Hasan | #2, #3 BAGRU instead of #1, #2 BAGRU
97 | Call-out |  | Ali Hasan | The maximum operating capacity of the Sulphur Plant is 790 MTPD: 1SRU: 170 MT/day 2SRU: 170 MT/day 3SRU: 225 MT/day 4SRU: 225 MT/day
98 | Call-out |  | Ali Hasan | #2, #3 BAGRU instead of #1, #2 BAGRU
99 | Call-out |  | Ali Hasan | TGTU instead of TGT
100 | Call-out |  | Ali Hasan | 4A CDU maxmium operating capacity is 105 MBPD, not 85 MBPD
101 | Text Box |  | Mahdi Ali | All unit abbreviations shall comply with BMPS-A8 Part B Appendix 1.
102 | Cloud |  | Mahdi Ali
103 | Cloud |  | Mahdi Ali
104 | Cloud+ |  | Mahdi Ali