## 000-A-PRO-50045-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp | Page 1 | Jawad Alawi
2 | Text Box | Page 7 | Jeung.Kim | Please include the scope split for the vendor data review with including details of engineering and procurement scope, such as sub-vendor list, inspection and testing, welding, inspection or packing and shipping.
3 | Rectangle | Page 8 | Jeung.Kim
4 | Strikethrough | Page 8 | Jeung.Kim
5 | Text Box | Page 8 | Jeung.Kim | The LLI has to be verified and agreed with Client
6 | Arrow | Page 8 | Jeung.Kim
7 | Text Box | Page 8 | Jeung.Kim | Please specify how to coordinate with OC's to issue the same type of MR in the same time in order to combine those by JVD.
8 | Cloud | Page 9 | Jeung.Kim
9 | Arrow | Page 9 | Jeung.Kim
10 | Text Box | Page 9 | Jeung.Kim | suggested to provide more details- what is the agreed splitting of scope of work?
11 | Arrow | Page 9 | Jeung.Kim
12 | Callout | Page 10 | peter.gilzean
13 | Note | Page 10 | peter.gilzean | Vol 2.6.5 1.2 requires Contractor to "develop a specific Bahraini content Purchasing Plan for Owner Review....." Timing for submission of such plan to be agreed by Owner/Contractor
14 | Callout | Page 10 | peter.gilzean
15 | Note | Page 10 | peter.gilzean | ..."Further details are as defined in the Deed Of Amendment dated 13 February 2018
16 | Note | Page 10 | peter.gilzean | Reference to investigating the possibility of procuring up to $200,000,000 of goods and services from eligible UK suppliers
17 | Note | Page 10 | peter.gilzean | Reference to the inclusion of at least 3 Vendors from the BMP AVL
18 | Note | Page 10 | peter.gilzean | Specific additional procedures procedures for the PSA Units
19 | Cloud | Page 11 | Jeung.Kim
20 | Text Box | Page 11 | Jeung.Kim | Contractor has to verify these criticality for Client agreement.
21 | Arrow | Page 11 | Jeung.Kim
22 | Note | Page 12 | peter.gilzean | In such instances, Contractor will assemble and pass qualification supporting documentation to Owner in parallel with the tendering cycle for review/approval
23 | Text Box | Page 12 | Jeung.Kim | Add "Minimize the number of vendor for same equipment for the favor of Client Interchangeability
24 | Note | Page 12 | peter.gilzean | and Technology Licensors as applicable
25 | Note | Page 12 | peter.gilzean | as described in Vol.2 6.5
26 | Note | Page 12 | peter.gilzean | as described in Vol.2 Section 6.5
27 | Note | Page 12 | peter.gilzean | Contractor is requested to refer to Vol.2 6.5 1.6 and ensure that all key elements from 1.6.1 to 1.6.19 are addressed in this Execution Plan
28 | Note | Page 14 | peter.gilzean | At the appropriate point in the Plan add text to cover Subcontractor Representatives and Specialists as referred to in Vol.2 6.5 1.151 to 1.15.7
29 | Note | Page 15 | peter.gilzean | As extracted from Volume 2.6.5 Section 1.7, add into the text of this Section or elsewhere in the document where relevant. Some of the current text may have to be altered . " For all equipment, as detailed within the Owners Requirements, Specification ref. BMPS-A7 Project Management and Handover (PIMH), Contractor shall present the following for the Owner and/or Licensor review and approval prior to placing any Purchase Orders (MPO) a) a copy of the Purchase Requisition (full set of documents issued for quotation requests) b) Prior to issuance of the MPO, Contractor shall provide an un-priced copy of the MPO for all equipment for Owner and/or Licensor review and approval.The un-priced copy of the MPO shall also include the Commercial Bid Analysis (CBE) to ensure that full compliance with Contract Terms and Conditions/schedule is adhered to. c) Contractor shall present a comprehensive un-priced Technical Bid Evaluation (TBE) with the deviation list (if any) for all equipment to the Owner and/or Licensor, for review and approval prior to proceeding with the Purchase order (MPO) issue.Owner and/or Licensor will conduct reviews and confirm to Contractor its approval prior to Contractor issuing any MPO. The TBE must include a complete unpriced technical evaluation of all aspects of the Request for Quotation and full comparison to the specifications. Any and all exceptions to the Contract, if applicable, shall be clearly identified. d) After quotations have been received for engineered plant and major bulk material purchases, but prior to award of MPOs, Contractors technical and commercial personnel and bidders shall hold technical bid clarification meetings, as required, to confirm compliance with Specifications. Owner shall be invited to attend technical bid clarification meetings . Additional meetings with bidders shall be conducted as requested by Owner. e)At the appropriate time after award of the MPOs for engineered Plant, design co-ordination/audit and pre-inspection meetings shall be held among Contractors technical and commercial personnel and Sub-contractors. Contractor shall advise Owner and Owner may decide to attend such meetings.
30 | Call-out | Page 16 | Jawad Alawi | Replace : may with shall
31 | Text Box | Page 18 | Harshad.K.Patel | Bapco should be involved for the review of short listed vendors TBT
32 | Note | Page 20 | peter.gilzean | See Vol.2 6.6 Section 1.6.13 (Purchasing) Site and in particular 1.6..13 f.
33 | Note | Page 21 | peter.gilzean | Refer to Volume 2 .6.5 1.9 to 1.14 and ensure all points contained therein are addressed/incorporated. This also applies to 000-A-PRI-50006-001-RA-.PDF included in this transmittal
34 | Note | Page 24 | peter.gilzean | Refer to Volume 2 6.5 1.8.1 and 1.8.2 requirements
35 | Note | Page 27 | peter.gilzean | review Vol 2 6.5 1.10 -1.14 for compliance with requirements
36 | Text Box | Page 38 | Jeung.Kim | Again, Contractor has to verify these criticality for Client agreement.
37 | Callout | Page 42 | Harshad.K.Patel | This should be for Review (Typical for all OCs)
38 | Text Box | Page 42 | Jeung.Kim | Most of the contents in this page is illegible! Please attached legible block diagram!- same for next page
39 | Callout | Page 43 | Harshad.K.Patel | This should be for Review