## 000-A-PRO-50052-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 11 | scott.hillman | "Branches/Families" - use consistent/formal language.
2 | Note | 11 | peter.gilzean | "that will be issued" Nothing to review
3 | Callout | 3 | Bernard.Grace | a High level
4 | Callout | 3 | scott.hillman | A number of documents are "referenced in this CEP that are not given reference numbers, or included in this list. In addition a number of documents need to be referenced here. These include, but are not limited to: - Commissioning and Pre-commissioning - Security Plan (to be provided as a seperate document) - Materials Management procedure - Quality Plan - Inspection Coordination Procedure
5 | Text Box | 2 | scott.hillman | As a general note, for ease of referencing, the document numbering should extend down to sub-sections, paragraphs etc. Numbering to Section level is insufficient. No definition is provide on Mechanical Completion, or use of checklists (API 700) Document includes a number of spelling and grammatical errors - Contractor to ensure adequate self checking and internal reviews before issuing.
6 | Text Box | 4 | Mahdi Ali | Avoid using the word 'New' as per BMPS-A8
7 | Call-out | 8 | Mahdi Ali | Bapco document number does not include revision
8 | Callout | 7 | scott.hillman | Be specific (general note, relevant to the entire document)
9 | Text Box | 12 | scott.hillman | Define how contractor productivity expectations will differ between areas.
10 | Callout | 11 | scott.hillman | Define TCF in section 3
11 | Text Box | 13 | scott.hillman | Define the timing and methodology for the constructibility workshops
12 | Text Box | 13 | scott.hillman | Define the timing for constructibility input (30% model reviews etc.)
13 | Callout | 7 | scott.hillman | Define these indicators. "leading/lagging" Include in definition section.
14 | Callout | 13 | scott.hillman | Define these.
15 | Callout | 11 | scott.hillman | Define what the differences are in the approach, and how they will be managed.
16 | Text Box | 5 | Jeung.Kim | General comment: please check this breakdown with latest WBS.- in order to calculate the progress based on level 3 or 4 schedule, it is strongly recommended to match this breakdown with schedule WBS.
17 | Text Box | 6 | Jeung.Kim | General comment: suggest the Safety and Quality to be independent from the area construction manager to avoid conflict of interest in the course of construction- refer to yellow shading in section 7.
18 | Callout | 4 | Nalini Mohan | H2 Plant
19 | Text Box | 12 | scott.hillman | Identify the major subcontracts that will be awarded, including the scope of work
20 | Callout | 13 | scott.hillman | Include definition of CWP and CWA in section 3. List the major Work Packages
21 | Text Box | 10 | scott.hillman | Include definition of schedule "level". Include types and frequency of reports to be prepared for construction phase.
22 | Note | 10 | peter.gilzean | Insufficient detail for review
23 | Text Box | 3 | scott.hillman | It is expected that as the amount of detail in the document expands the definition section will also expand, significantly.
24 | Call-out | 4 | Hasan Al Noaimi | No 3 Sulphur Plant
25 | Text Box | 5 | scott.hillman | Provide a list with unit numbers linked to a description of the unit, or a reference document.
26 | Callout | 12 | scott.hillman | Provide a proper breakdown, by unit and work pack, identifying what is being treated as brownfield and what is being treated as greenfield.
27 | Callout | 9 | scott.hillman | Provide a reference number for this document and include in the reference section.
28 | Callout | 4 | scott.hillman | Provide detailed unit/workpage list, as per drawing BRA-229583
29 | Callout | 11 | scott.hillman | Provide details of this organization including an org chart and roles/responsibilities
30 | Callout | 14 | scott.hillman | Provide details of this, including the organization structure.
31 | Text Box | 12 | scott.hillman | Provide details on the extent/use of subcontractors.
32 | Callout | 12 | scott.hillman | Provide details/references etc.
33 | Callout | 7 | scott.hillman | Provide reference number
34 | Text Box | 2 | Terence.Lyons | Recommend Author refers BPM Vol 2; Common Documents and Requirements Section 1.1 Project Instructions. There is no requirement for a HSSE Plan as referred to within the supplied Construction Execution Plan Refer to Page 17.1.2 Responsibilities In order to achieve the above mentioned targets, Contractor shall submit to Owner its own Health, Safety and Environment System, within eight (8) weeks from Effective Date of Contract, which shall comply with all the applicable national and international laws and regulations and cover Owner HSE requirements as minimum (see paragraph 10.1 of this Volume 2 for the Site HSE Plan). VOLUME 2 – COMMON DOCUMENTS AND REQUIREMENTS EXHIBIT 6 - CONTRACTOR DOCUMENT REQUIREMENTS LIST (CDRL) Page 11 of 57 Item A2.19 Security Plan Volume 2-Common Documents and Requirements, details the specific HSE and Security information required to be included in the Construction Execution Plan.
35 | Text Box | 8 | scott.hillman | There is no mention of safety inductions, start cards, mandatory JHA's, RAMS, etc
36 | Callout | 11 | scott.hillman | There is no reason these deliverables cannot be defined and referenced in this CEP.
37 | Callout | 14 | scott.hillman | This conflicts with the statement on Page 15
38 | Text Box | 1 | scott.hillman | This document has been rejected on the basis that it fails to comply with the requirements for a CEP, set out in Vol.2, Section 1.1 (Owners Instructions), Paragraph 15 (Construction and Installation). Paragraph 15 details the expectations for the Construction Management of the BMP, and includes the minimum requirements for the Construction Execution Plan in paragraph 15.1. The comments on this revision shall not be considered an exhaustive list, and does not absolve the Contractor of it's responsibility to satisfy themselves of that they have met the required standard established in Vol2. Section 1.1 Paragraph 15. The Contractor is also directed to Vol2. Section 6, Sub-section 6.6 for guidance on the content of the CEP.
39 | Callout | 1 | Bernard.Grace | This document is very generic with insufficeint details on the methadology for executing the works to permit review
40 | Text Box | 9 | Mahdi Ali | This documents does not include the Summer working hours according to Bahrain Labour Law
41 | Text Box | 14 | scott.hillman | This list is far to brief. "Site Activites" should be split sections by trade/disipline or area, and comprehensive list of the activities provided, even if it is intended to be a "guide"
42 | Callout | 16 | Abdul Rahim | This needs to be expanded by stating how construction execution plans will be developed, surely not all works at Wharf will be given to subcontractor
43 | Text Box | 11 | scott.hillman | This section needs to be more specific and a mobilization plan is required. Include definition of Early Works in Section 3.
44 | Callout | 3 | scott.hillman | Use on description, should be in-line with the Contract definitions
45 | Callout | 14 | scott.hillman | What about geotechnical /topo/TCF/temporary roads etc etc.
46 | Callout | 11 | scott.hillman | What is "first" Contractor?
47 | Text Box | 15 | scott.hillman | What is the status of the above activities - Specific detail is required about how the job will be managed, not initiatives that may or may not be pursued.