## 000-A-RPT-60001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdulla Al Ansari | For clarity purpose and to avoid any confusion, the document title across this document to be replaced with "BMP ESIA"
2 | Callout | 2 | Abdulla Al Ansari | Chance it to BMP ESIA
3 | Callout | 2 | Abdulla Al Ansari | To be corrected to OESMP
4 | Callout | 8 | Abdulla Al Ansari | This statement is not entirely correct, please revise it and update as necessary in terms of permitting responsibilities in accordance to EPC Contract, Owner Consents and Contractor Consents.
5 | Callout | 8 | Abdulla Al Ansari | A statement to be incorporated to highlight that this report and its attachments will be updated and issued on regular basis to the BMP
6 | Callout | 8 | Abdulla Al Ansari | To be replaced with "also provide"
7 | Callout | 10 | Abdulla Al Ansari | Clarify this action item for reference
8 | Callout | 10 | Abdulla Al Ansari | Clarify this action item for reference
9 | Callout | 10 | Abdulla Al Ansari | Replace it with: the allocated tanks (Tanks 915 & 710)
10 | Callout | 10 | Abdulla Al Ansari | Change to: published in designated website
11 | Callout | 10 | Abdulla Al Ansari | Relevant closure metric should be filled out
12 | Callout | 10 | Abdulla Al Ansari | Change to: to be reviewed and approved
13 | Callout | 10 | Abdulla Al Ansari | Include: BMP EHS Coordinator
14 | Callout | 10 | Abdulla Al Ansari | Add: However, CESMP and OESMP are expected to be updated at detail design
15 | Callout | 10 | Abdulla Al Ansari | Replace FEED ESIA with BMP ESIA
16 | Callout | 10 | Abdulla Al Ansari | Include as a remark: Currently, BAPCO is issuing GHG Inventory Report according to NOGA requirements
17 | Callout | 10 | Abdulla Al Ansari | Suggest to be reworded as: investigate and confirm that the allocated tanks are designed in line with ESIA requirements and provided with
18 | Callout | 11 | Abdulla Al Ansari | add: Managament
19 | Callout | 11 | Abdulla Al Ansari | Please confirm if OESMP or CESMP. Also, include ESAP as a source for this requirement
20 | Callout | 11 | Abdulla Al Ansari | Include: Updated H&S standards and procedures. Updated Manual and related procedures of OHSAS 18001
21 | Callout | 11 | Abdulla Al Ansari | Include: Annual Waste Compliance Reporting to SCE
22 | Callout | 11 | Abdulla Al Ansari | Add: and Detail Design
23 | Callout | 11 | Abdulla Al Ansari | To be corrected as From
24 | Callout | 11 | Abdulla Al Ansari | This statement need to be rephrased for clarity
25 | Callout | 11 | Abdulla Al Ansari | Insert: BMP EHS Coordinator/Engineering Manager - O&U/PC&I Lead Engineer
26 | Callout | 12 | Abdulla Al Ansari | EIS to be issued to SCE
27 | Callout | 12 | Abdulla Al Ansari | Include: Updated environmental site investigation of Pitch Ponds
28 | Callout | 12 | Abdulla Al Ansari | Delete Marine
29 | Callout | 12 | Abdulla Al Ansari | Is this plan different than Project Environmental Plan
30 | Callout | 12 | Abdulla Al Ansari | Replace with: details
31 | Callout | 12 | Abdulla Al Ansari | Delete Marine
32 | Callout | 12 | Abdulla Al Ansari | Please confirm if de-watering to Maameer Channel is permitted, accordingly this item should be revised
33 | Callout | 12 | Abdulla Al Ansari | The text is cropped, to be fixed
34 | Callout | 12 | Abdulla Al Ansari | Merge with Item 33 above due to similar objective
35 | Callout | 13 | Abdulla Al Ansari | Item 64 to be merged with a previous relevant similar item due to similar objective
36 | Callout | 13 | Abdulla Al Ansari | Add: To be established
37 | Callout | 13 | Abdulla Al Ansari | Include: HSSE Requirements for Vendors and Sub-contractors
38 | Callout | 13 | Abdulla Al Ansari | Include: ESAP
39 | Callout | 14 | Abdulla Al Ansari | Replace "Environmental" with "Waste"
40 | Callout | 14 | Abdulla Al Ansari | Add: /BMP EHS Coordinator
41 | Callout | 14 | Abdulla Al Ansari | Add: /BAPCO
42 | Callout | 15 | Abdulla Al Ansari | Delete number 10
43 | Callout | 15 | Abdulla Al Ansari | Include: and Construction
44 | Callout | 15 | Abdulla Al Ansari | Include: /TTS JV
45 | Callout | 15 | Abdulla Al Ansari | To be filled out with appropriate info
46 | Callout | 15 | Abdulla Al Ansari | Delete number 22
47 | Callout | 18 | Abdulla Al Ansari | Delete Lenders' Advisor
48 | Callout | 18 | Abdulla Al Ansari | Delete Lenders' Advisor
49 | Callout | 18 | Abdulla Al Ansari | To be corrected to EIA-9 Guidelines
50 | Call-out | 3 | Edgardo | insert "Techicas Reunidas"
51 | Call-out | 5 | Mahdi Ali | Do not use FEED numbers. use Bapco numbers instead
52 | Call-out | 10 | Mahdi Ali | Avoid using the word 'New' as per BMPS-A8
53 | Callout | 3 | Mohamed Ghassan | Insert "modernizing and expanding" rather than only "modernizing"
54 | Callout | 3 | Mohamed Ghassan | change "recommendations" to "requirements and recommendations"
55 | Callout | 3 | Mohamed Ghassan | please replace "any additional requirements" with "adherence to any additional requirements"
56 | Callout | 3 | Mohamed Ghassan | Please replace "IFC performance standards and IFC guidelines" with "IFC Performance Standards and guidelines as well as the Equator Principles"
57 | Callout | 3 | Mohamed Ghassan | replace "BMP Environmental Permit" with "attaining any/all required environmental permits"
58 | Callout | 3 | Mohamed Ghassan | Please replace "ECAs" with "Export Credit Agencies (ECAs)"
59 | Callout | 6 | Mohamed Ghassan | please replace the highlighted text with "includes all required mitigation measures and monitoring requirements identified during the FEED phase of the project. However, like the CESMP the OESMP is a "living" document and will be updated as and when required throughout the duration of the project."
60 | Callout | 6 | Mohamed Ghassan | Please include a statement in this section to say that the CESMP is a "living" document and such will be updated as and when required throughout the duration of the project
61 | Callout | 10 | Mohamed Ghassan | Please add OESMP Table 4.2 (Operational Phase Management and Mitigation Requirements) and Please add ESIA Table 16.6 (Operational Phase Risk Assessment â€“ Crude Oil, Intermediates and Products Storage)
62 | Callout | 10 | Mohamed Ghassan | Please add: 1. Air Pollution Source Quality Compliance Report 2. Ambient Air Quality Compliance Report
63 | Callout | 10 | Mohamed Ghassan | See earlier comments related to acronyms.
64 | Callout | 10 | Mohamed Ghassan | While relevant requirement will be placed on contractors, it is also important for TTSJV to present how they will assess and identify high risk sub-contractors/suppliers/vendors.
65 | Callout | 10 | Mohamed Ghassan | While this item is closed for the camp 1 site, section 12.6 of the ESIA, which is concerned which states the mitigation measures related to the protection of terrestrial ecology , states that, "Within the Ma'ameer Channel, the construction compound should be carefully sited to avoid damage to the shoreline habitat and islets." Please update accordingly.
66 | Callout | 10 | Mohamed Ghassan | Please state/explain what D/S is. Only use acronyms listed in the acronym list.
67 | Callout | 10 | Mohamed Ghassan | Capital letter... To be
68 | Callout | 10 | Mohamed Ghassan | Please add RFQ to the acronyms list. Only use acronyms listed in the acronym list.
69 | Callout | 10 | Mohamed Ghassan | These are simply the relevant engineering standards and do not present appropriate closure metrics. The closure metric should be a demonstration that the design is in line with best practices in E&S Study #26 and the Ambient Air Quality Compliance Report. Please replace with a more suitable closure metric.
70 | Callout | 10 | Mohamed Ghassan | Please add the following: 1. Air Pollution Source Quality Compliance Report 2. Ambient Air Quality Compliance Report 3. Waste Water Discharge Quality Compliance Report
71 | Callout | 11 | Mohamed Ghassan | Please insert "Updated/post-BMP Refinery Waste Management Plan"
72 | Callout | 11 | Mohamed Ghassan | Section cropped out. Please fix.
73 | Callout | 11 | Mohamed Ghassan | The main details should be summarized here, while still referencing the original text for further details.
74 | Callout | 11 | Mohamed Ghassan | Please add GMP to acronym list.
75 | Callout | 11 | Mohamed Ghassan | Text was cropped out. Please fix.
76 | Callout | 11 | Mohamed Ghassan | Please add detailed engineering
77 | Callout | 12 | Mohamed Ghassan | The closure metric for this is not the ESAP, it is the validation report to be conducted by EAC. Please amend to reflect this.
78 | Callout | 12 | Mohamed Ghassan | Please replace "contaminated" with "contamination"
79 | Callout | 12 | Mohamed Ghassan | Please include a brief summary of the points from section 7.6.3.2 while still including reference to it for further details.
80 | Callout | 12 | Mohamed Ghassan | Please include a brief summary of the points from section 8.6.1 while still including reference to it for further details.
81 | Callout | 13 | Mohamed Ghassan | Please add; ensure complete compliance with section 4.9 of the CESMP.
82 | Callout | 13 | Mohamed Ghassan | Please add periodic monitoring to the closure metrics fro this item.
83 | Callout | 13 | Mohamed Ghassan | For the sake of clarity, please add a short statement to explain the difference between the transport and traffic management plans.
84 | Callout | 14 | Mohamed Ghassan | Please replace "LDRA" with LDAR
85 | Callout | 14 | Mohamed Ghassan | Please add "and with inputs from TTS JV" after "Environmental Consultant"
86 | Callout | 14 | Mohamed Ghassan | Please add OESMP
87 | Callout | 14 | Mohamed Ghassan | Please change to "Updated/post-BMP Refinery Waste Management Plan"
88 | Callout | 14 | Mohamed Ghassan | Please replace "BAPCO" with "TTS JV/BAPCO"
89 | Callout | 14 | Mohamed Ghassan | Section cropped out, please fix.
90 | Callout | 14 | Mohamed Ghassan | Please replace with "Updated OESMP"
91 | Callout | 14 | Mohamed Ghassan | TTS JV is to update the plan while Bapco is to implement it during operation.
92 | Callout | 15 | Mohamed Ghassan | This is applicable due to radioactive materials used in RHCU gauges. Please revise action status and closure metric to reflect this.
93 | Callout | 15 | Mohamed Ghassan | Please replace "closed" to "to be developed"
94 | Callout | 15 | Mohamed Ghassan | Please replace "during CESMP and OESMP" with "during CESMP & OESMP audits"
95 | Callout | 15 | Mohamed Ghassan | Please add "Environmental Approval From SCE" with the Permitting Plan
96 | Callout | 15 | Mohamed Ghassan | For all three of these items please include the timescale of when they are to be done.
97 | Callout | 15 | Mohamed Ghassan | Please replace "Operation" with "Construction & Operation"
98 | Callout | 15 | Mohamed Ghassan | Please replace "Operation" with "Construction & Operation"
99 | Callout | 15 | Mohamed Ghassan | Please replace "BAPCO" with "TTS JV/BAPCO"
100 | Callout | 3 | Muhammad.N.Asim | Replace CEMP with Construction Environmental and Social Management Plan (CESMP)
101 | Callout | 3 | Muhammad.N.Asim | delete "expansion program"
102 | Callout | 3 | Muhammad.N.Asim | Replace EMP with Operational Environmental and Social Management Plan (OESMP)
103 | Callout | 3 | Muhammad.N.Asim | Replace "CEMP and OEMP" with "CESMP and OESMP"
104 | Callout | 3 | Muhammad.N.Asim | add here "in Environmental and Social Due Diligence (ESDD)" add ESDD in Acronyms
105 | Callout | 3 | Muhammad.N.Asim | Replace "of" with "for"
106 | Callout | 3 | Muhammad.N.Asim | Replace "BMP expansion program" with "Bapco Modernization Program (BMP)"
107 | Callout | 3 | Muhammad.N.Asim | Replace "BMP's ESIA" with "BMP ESIA mitigation measures"
108 | Callout | 4 | Muhammad.N.Asim | Replace "Environmental Social" with "Environmental and Social"
109 | Callout | 4 | Muhammad.N.Asim | Replace "Environmental Social" with "Environmental and Social"
110 | Callout | 4 | Muhammad.N.Asim | Replace "BMP Expansion program" with "BMP" as BMP stands for Bapco Modernization Program
111 | Callout | 4 | Muhammad.N.Asim | Replace "of" with "for"
112 | Callout | 5 | Muhammad.N.Asim | insert "and Social"
113 | Callout | 6 | Muhammad.N.Asim | Change "CESMP" with "OESMP"
114 | Callout | 7 | Muhammad.N.Asim | Replace "of with "For"
115 | Callout | 10 | Muhammad.N.Asim | Replace "Air Quality direct stack emission" with "Stack Emissions"
116 | Callout | 10 | Muhammad.N.Asim | Replace "Air Quality GHG with "Greenhouse Gas (GHG) Emissions'
117 | Callout | 10 | Muhammad.N.Asim | please replace the word "greater" with "more stringent"
118 | Callout | 10 | Muhammad.N.Asim | "BMP ESIA"
119 | Callout | 10 | Muhammad.N.Asim | text is missing
120 | Callout | 11 | Muhammad.N.Asim | Replace "contraction" with "Construction"
121 | Callout | 11 | Muhammad.N.Asim | Replace "ny" with "any"
122 | Callout | 14 | Muhammad.N.Asim | insert "and Social"
123 | Callout | 14 | Muhammad.N.Asim | Replace Early with "yearly"
124 | Callout | 14 | Muhammad.N.Asim | Replace "environmental management plan" with "CESMP & OESMP"
125 | Callout | 15 | Muhammad.N.Asim | Kindly consider the aspects of Workers Camps operations e.g wastewater treatment, solid waste management.
126 | Callout | 17 | Muhammad.N.Asim | delete "SCE"
127 | Callout | 17 | Muhammad.N.Asim | Requirements are not set by SCE for Fence line Benzene Monitoring. This is lenders requirement. Please delete "SCE"
128 | Callout | 17 | Muhammad.N.Asim | insert "and IFC /EBRD standards"
129 | Callout | 17 | Muhammad.N.Asim | Fugitive Emission monitoring reports would not be required to submit SCE.
130 | Callout | 17 | Muhammad.N.Asim | Not required to report SCE. Please delete.
131 | Callout | 17 | Muhammad.N.Asim | Not required to report SCE. Please delete
132 | Callout | 17 | Muhammad.N.Asim | This is Occupational Health Monitoring or Exposure Assessments. OHS matters reporting to SCE is not required.
133 | Callout | 17 | Muhammad.N.Asim | Please delete "during first 6 months operation"
134 | Callout | 17 | Muhammad.N.Asim | For Wastewater discharge, please use the word "effluent monitoring" instead of "emissions"
135 | Callout | 18 | Muhammad.N.Asim | Please delete " SCE" as this is lenders requirement not SCE.
136 | Call-out | 4 | Rashed Almudahka | replace front end engineering with front end engineering Design
137 | Callout | 4 | Robert.Kawitzki | Delete space
138 | Callout | 4 | Robert.Kawitzki | Delete space
139 | Callout | 5 | Robert.Kawitzki | Delete dash - typ comment