## 000-A-SCH-50001-001-R0-bb comme
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box |  | Sankara | This document cannot be meaningfully reviewed in absence of a clear definition of the work packages. e.g. WPA, WPB etc.
2 | Callout |  | david.huggins | Please note that all comments made on this document shall be considered and discussed with Owner's Project Control team for next issue of the 90 Day Starter schedule
3 | Stamp |  | david.huggins
4 | Text Box |  | Harshad.K.Patel | Not all Execution Plans included (e.g. Engineering Management, Quality Management, Interface Management etc.)
5 | Callout |  | Harshad.K.Patel | Show weekends & Holidays
6 | Text Box |  | Jeung.Kim | Also HSE Plan missed
7 | Rectangle |  | Jeung.Kim
8 | Arrow |  | Jeung.Kim
9 | Text Box |  | Jeung.Kim | Seem incomplete or missing some words
10 | Arrow |  | Jeung.Kim
11 | Text Box |  | Jeung.Kim | IFR
12 | Arrow |  | Daniella.Botta
13 | Text Box |  | Daniella.Botta | Project controls and procurement specific procedures missing
14 | Text Box |  | Daniella.Botta | Detailed training plan described in annex 12 exhibit F is missing
15 | Text Box |  | Daniella.Botta | Knowledge Transfer, Learning and Training Program described in annex 12 exhibit F is missing
16 | Text Box |  | Daniella.Botta | Organization procedure of the supply of Goods, inspection of Goods, follow-up and dispatching of Goods is missing
17 | Arrow |  | Daniella.Botta
18 | Text Box |  | Daniella.Botta | Due date according to contract is March 28, 30 days after ED
19 | Arrow |  | Daniella.Botta
20 | Text Box |  | Daniella.Botta | Due date according to contract is March 12, 14 days after ED
21 | Arrow |  | Daniella.Botta
22 | Text Box |  | Daniella.Botta | Due date according to contract is March 28, 30 days after ED
23 | Text Box |  | Daniella.Botta | Activity missing for level 3/4 and onward weight factors for home office activites, due date march 26, 28 days after ED
24 | Arrow |  | Daniella.Botta
25 | Text Box |  | Daniella.Botta | due date according to contract is march 26, 28 days after ED
26 | Arrow |  | Daniella.Botta
27 | Text Box |  | Daniella.Botta | Due date according to contract is march 12, 14 days after ED
28 | Arrow |  | Daniella.Botta
29 | Text Box |  | Daniella.Botta | HSE procedure is missing
30 | Text Box |  | Daniella.Botta | Activity for test plans missing
31 | Text Box |  | Daniella.Botta | Activity missing for submittal of procedures to implement and maintain a complete control system the receipt, inspection, protection, preservation, care and custody, issuance out and inventories of all Goods consigned to Site or other areas of the project
32 | Arrow |  | Daniella.Botta
33 | Text Box |  | Daniella.Botta | Clarify
34 | Arrow |  | Jeung.Kim
35 | Text Box |  | Jeung.Kim | Please use English!
36 | Arrow |  | Jeung.Kim
37 | Text Box |  | Jeung.Kim | General comment: The issue of MDS and MR before issuing of their related precedent process design will be reviewed only for LLI or schedule critical items under condition that the design parameter related with process design will be verified before placing purchase order. All other items will be issued with engineering logical sequence.
38 | Arrow |  | Jeung.Kim
39 | Text Box |  | Jeung.Kim | If it is piping material class specification, it should be issued after first issue of P&ID.
40 | Callout |  | Harshad.K.Patel | NO instrumentation related deliverables included for any WPs - Please confirm.
41 | Callout |  | rob.urban | PFD issue not realistic considering changes in RHCU
42 | Arrow |  | Jeung.Kim
43 | Text Box |  | Jeung.Kim | What is tthe definition of these WBS, WPB, C, D, E...?
44 | Arrow |  | Jeung.Kim
45 | Text Box |  | Jeung.Kim | Definition?
46 | Callout |  | rob.urban
47 | Callout |  | rob.urban | Schedule is shown as bars where it can not been seen when a document is issued. For instance issue of equipment list or PFD's IBD should be one date not a period
48 | Text Box |  | Jeung.Kim | General Comments: 1. Are all these items LLI or schedule Critical items? Except LLI and Critical items, mechanical Data sheet and Material Requisition have to be issued after precedent process design is completed and reviewed by Client. Also the LLI and Schedule Critical items have to be confirmed its criticality in the schedule. 2. Is the issue of both MDS and MR in the same time agreed with Client? Is that only for LLI and Critical items? Otherwise it has to be agreed with Client for its procedure.
49 | Callout |  | james.wright | FS positive lags need to be avoided. They do not allow for true analysis of float. Remove where possible and add activities with FS Zero positive lag relationships. Note: For the level 3 Master Schedule "no" FS positive lags will be accepted
50 | Text Box |  | Robert.Kawitzki | Timing for Piping Spec and OA Plot Plan seems to be too tight
51 | Arrow |  | Jeung.Kim
52 | Text Box |  | Jeung.Kim | Does this finish date mean the first issue date?