## 000-C-GRD-60001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box |  | Ravi Kumar | All Licensors Drawings, Specifications, Reference Drawings related to HP Vessels not issued alongwith this transmittal should be included in the MR
2 | Stamp |  | Ravi Kumar
3 | Text Box |  | Ravi Kumar | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3
4 | Call-out |  | Ali Abbas
5 | Call-out |  | Ali Abbas
6 | Call-out |  | Ali Abbas
7 | Call-out |  | Ravi Kumar | There is no order of precedence within the technical documents as per Annex 1 of the contract.
8 | Callout |  | Fatema Hashem | 1. AND AS PER CLG LC-FINING INTERSTAGE SEPERATOR DESIGN SPECIFICATIONS 191807-D-265 SHT 1-11
9 | Cloud |  | Fatema Hashem
10 | Cloud |  | Fatema Hashem
11 | Callout |  | Fatema Hashem | 1. AND AS PER CLG LC-FINING HPHT SEPERATOR DESIGN SPECIFICATIONS 191807-D-266 SHT 1-11
12 | Cloud |  | Fatema Hashem
13 | Cloud |  | Fatema Hashem
14 | Callout |  | Fatema Hashem | 1. AND AS PER CLG LC-FINING HPHT SEPERATOR DESIGN SPECIFICATIONS 191807-D-266 SHT 1-11
15 | Callout |  | Fatema Hashem | 1. AND AS PER CLG LC-FINING INTERSTAGE SEPERATOR DESIGN SPECIFICATIONS 191807-D-265 SHT 1-11
16 | Call-out |  | Ravi Kumar | PTC-601 is not part of the transmittal issued for review and hence not reviewed
17 | Call-out |  | Ravi Kumar | It is mentioned "vendor list below" - not found in the transmittal issued for review
18 | Call-out |  | Jawad Alawi | Why only manual?
19 | Text Box |  | Jawad Alawi | Third party agency need to be approved by owner
20 | Call-out |  | Hasan Al Noaimi | I think 2 years as per gurantee.
21 | Call-out |  | Ali Hasan | 2-years Operational spares are required as stated in para 10.2 below.
22 | Cloud |  | Ali Hasan