## 000-C-GRD-70004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | always add document title in the header
2 | Text Box | 1 | Mahdi Ali | what is the equipment number
3 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all pages
4 | Text Box | 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
5 | Text Box | 4 | Antony.Bentley | Seismic not applicable
6 | Call-out | 4 | Ahmed Marhoon | Add a note to the suppliers on possibility of modifications in the instrument nozzles details that may occur as a result of Hazop/SIL recommendation and/or EPC design development.
7 | Text Box | 5 | Mahdi Ali | remove revision from the document number. add revision 'A' instead.
8 | Cloud+ | 5 | bapco-user | 019V0003 and 019V0010 and also correct the other numbers in this page
9 | Callout | 6 | Mohamed Ayyash | Two (Tyop)
10 | Call-out | 7 | Ali Abbas | Note: The Nozzles and Connections location for instrumentations shall be confirmed once level measurement type, range and installations are finalized.
11 | Callout | 7 | Adnan Alothman | Typo - 4
12 | Text Box | 9 | Mahdi Ali | remove revision from the document number. add revision 'A' and revision 'B' instead.
13 | Text Box | 10 | Mahdi Ali | remove revision from the document number. add revision 'A' instead.
14 | Callout | 13 | Mohamed Ayyash | Should read Commissioning and Start-up (not vise versa)
15 | Callout | 13 | Mohamed Ayyash | Add "Commissioning"
16 | Text Box | 13 | Hasan Asad | Spare parts shall include first run and T&I list of spares. SPIL sheet as per BMPS S-12 shall be provided.
17 | Callout | 14 | Mohamed Ayyash | Space
18 | Callout | 14 | Mohamed Ayyash | Is the commissioning phase included ?