## BAPCO DOC. CODE-REV-CS
ID N° | Subject | pages | Author | Comments | JV Replies | Comment Included (Y/N) | Bapco Closure (Y/N)
1 | Text Box |  | A.Jabbar Mahmood | All pages with odd numbers (starting from page 3) are missing. The document shall be resubmitted for Owner's review. | This could have been due to the document was printed on double face pages, of which may be it was made single face scanner, however the document was issued with all pages. | Y
2 | Call-out |  | Raj | Replace by 2HCU | Agreed. It will be included and updated in the next emission of the document. | Y
3 | Text Box |  | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3. | Agreed. It will be included and updated in the next emission of the document.
4 | Callout |  | A.Jabbar Mahmood | Ensure that the latest revisions of the drawings are included in 019C0001R-EW and 019C0002R-EW as per bidders query number T194 (revised mixing box design). Drawings RD-140557,RD-140580, RD-140581, RD-140584, RD-140594, RD-140617, RD-140618 and RD-140621 shall be rev 1. | Agreed. The latest revisions of the drawings have been included in DDSS for the Reactors HCU, which they've already been issued in Rev. A with the following documents number: 019-C-DAT-30001-001 for First Stage Reactor 019C0001R and 019-C-DAT-30002-001 for Second Stage Reactor 019C0002R | Y
5 | Cloud+ |  | A.Jabbar Mahmood | All these drawings have not been provided in this transmittal and hence not reviewed. | These drawings will be issued officially as per procedure. | Y
6 | Call-out |  | A.Jabbar Mahmood | PTC-604 has not included in this transmittal and hence not reviewed | This document will be issued in next emision. | Y
7 | Callout |  | Mohamed Ayyash | add . | Agreed.
8 | Callout |  | Mohamed Ayyash | space | Agreed.
9 | Callout |  | Mohamed Ayyash | , start up | Agreed. It will be included and updated in the next emission of the document.