## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
WHMJHGRXPQONTMAJ | Cloud+ | Ahmed Marhoon | Different addresses are being quoted on different documents issued by MOC. MOC to confirm. | Noted. It will be updated as per contract in revision A | Y
GVROBUJTUQIYBKZL | Text Box | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3. | Noted. | N
YVDZJXSBSVJTCSZP | Cloud+ | Ahmed Marhoon | TTSJV to ensure consistency between all documents in describing the JV structure. Should it read TechnipFMC instead of U.S.A and Italy?. TTSJV to confirm. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N
BEKZWHRGNJRLVIPD | Callout | Adnan Alothman | Change BMPS-C3 to BMPS-C2 | Noted. It will be implemented in revision A | Y
LJFGCVSRWPELNBWC | Callout | Adnan Alothman | Change BMPS-C3 to BMPS-C2 | Noted. It will be implemented in revision A | Y
FNZXSJIHIJGRGEFZ | Call-out | 986131 | The level of the tray support rings must be fabricated with the tolerance specified by the internal vendor. This comment is applicable for all the columns in this document. | Internals shall be designed by Internal Vendor (including tolerances) and Column Vendor will follow this design. | N
TJZYXGDVRUJOBRZS | Callout | Adnan Alothman | Correct document no. to GF-C13950 | Noted. It will be implemented in revision A | Y
KVITHYAJNLIGNWIL | Callout | Adnan Alothman | Correct document no. to GF-C13950 | Noted. It will be implemented in revision A | Y
HIJGDBVAYORRWIDK | Call-out | bapco-user | Change SR to SOW | Noted. It will be implemented in revision A | Y
PSYLWWATXQFUVWVI | Callout | Mohamed Ayyash | Add the word "commissioning" to this sentence. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N
UYDBGZRIGWXIVQMR | Callout | Mohamed Ayyash | Add the word "start up" to those sentences. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N