## 000-C-ITP-70004-001-RAP-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Casella di testo | 1 | LPetroni | AP | Agreed, corrected and updated. | Y
2 | Casella di testo | 1 | LPetroni | AP | Agreed, corrected and updated. | Y
3 | Casella di testo | 1 | LPetroni | ISSUE FOR INQUIRY-PENDING | Agreed, corrected and updated. | Y
4 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all pages | Agreed, this typo has already been corrected and updated. | Y
5 | Callout | 1 | bapco-user | Change Technip Italy to CONTRACTOR | Agreed, corrected and updated. | Y
6 | Casella di testo | 2 | LPetroni | AP | Agreed, corrected and updated. | Y
7 | Callout | 2 | bapco-user | Correct: and UT | Agreed, corrected and updated. | Y
8 | Callout | 2 | bapco-user | Add Before Fabrication | Agreed, included and updated. | Y
9 | Casella di testo | 3 | LPetroni | AP | Agreed, corrected and updated. | Y
10 | Callout | 3 | bapco-user | Missing for 019V0010 | Agreed, included and updated. | Y
11 | Casella di testo | 4 | LPetroni | AP | Agreed, corrected and updated. | Y
12 | Callout | 4 | bapco-user | Missing for 019V0010 | Agreed, included and updated. | Y