## 000-C-ITP-70009-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Yousif Ahmadi | Add "W" to fit up
2 | Callout | 2 | Yousif Ahmadi | Add to the stage: Before fabrication
3 | Call-out | 3 | 986131 | Add: Levelness checks for all Tray/packing support Ring and distributor supports.
4 | Callout | 1 | Yousif Ahmadi | Change Technip Italy to TR
5 | Callout | 4 | Yousif Ahmadi | Plates for Heads: Add HIC TEST
6 | Callout | 1 | Mohamed Ayyash | Project title should read " BAPCO MODERNIZATION PROGRAM"
7 | Callout | 4 | Yousif Ahmadi | Shell Plates: Add HIC TEST
8 | Cloud+ | 2 | Mohamed Ayyash | Text is misaligned horizontally. Correct for better representation. Apply to all pages.
9 | Callout | 1 | Mohamed Ayyash | This is a 5 page document and not 4. Apply to all pages
10 | Callout | 3 | Mohamed Ayyash | This page (page 3/5) has no heading. Need to adjust sheets layout.