## 000-C-ITP-70010-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | This is a 5 page document and not 4. Apply to all pages
2 | Callout | 1 | Mohamed Ayyash | Project title should read " BAPCO MODERNIZATION PROGRAM"
3 | Callout | 2 | Yousif Ahmadi | ADD: BEFORE FABRICATION
4 | Callout | 3 | Mohamed Ayyash | This page (page 3/5) has no heading. Need to adjust sheets layout.
5 | Call-out | 3 | 986131 | For Gravity distributors - Level test and Area test is required at the vendors workshop for minimum, normal and maximum rated flow for the distributors. Testing to include overflow rate for the distributors. This to be witnessed by owner representative. For Spray distributor - Area Coverage test at minimum, normal and maximum rate at vendors workshop. Testing to be witnessed by owner representative. For Tray and Packing - Mock assembly at the vendor workshop before dispatch to be witnessed by owner representative.
6 | Callout | 4 | Yousif Ahmadi | Add: UT examination "W"