## 000-C-MRQ-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Casella di testo | 1 | FMissanelli | H.P. VESSELS (LLI) | Noted
2 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets. | Noted. It will be updated in revision A | Y
3 | Cloud+ | 2 | A.Jabbar Mahmood | TR to provide these datasheets for owner's review. | Noted. It will be updated in revision A | Y
4 | Callout | 2 | Mohamed Ayyash | Delete part of the line for better representation | Noted. It will be updated in revision A | Y
5 | Call-out | 2 | Mahdi Ali | Incorrect sequence number | N/A | N
6 | Text Box | 5 | A.Jabbar Mahmood | Any applicable licensor specifications and standard drawings shall be included. | Noted, Already checked | N