## 000-C-MRQ-80004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
| Arrow | 1 | Jeung.Kim
1 | Text Box | 1 | Jeung.Kim | should be mechanical data sheet
| Arrow | 1 | Jeung.Kim
2 | Text Box | 1 | Jeung.Kim | Are these separate deliverables or part of this MR?- typical comment
3 | Text Box | 1 | Jeung.Kim | These MDS's have to be issued after issue and review of relevant precedent process designs in order to provide basis of these review and MR has to be issued after issue and review of MDS with same background.- this is typical comment for documents included in this MR.a
| Arrow | 1 | Jeung.Kim
4 | Callout | 2 | Julio.Aguilar | Add: BMPS-A1 and BMPS-A3