## 000-C-SOW-70003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets. | Noted. It will be updated in revision A | Y
2 | Text Box | 1 | MAK | Use the latest cover page template that is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N
3 | Cloud+ | 1 | Adnan Alothman | All vessels listed in this MR are CS vessels. TR to check and modify the title | This title is preffered in case a SS vessels need to be quoted in a future | N
4 | Callout | 3 | Yousif Ahmadi | Add: Equipment initial gauign reports | Noted. It will be updated in revision A | Y