## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box |  | Harshad.K.Patel | Please revise and re-submit PEP per comments shown on this document. | Agreed.
2 | Callout |  | Mohamed Ayyash | 2HCU | Agreed. This will be corrected and updated in next emission.
3 | Stamp |  | Raj
4 | Callout |  | Mohamed Ayyash | 2HCU | Agreed. This will be corrected and updated in next emission.
5 | Call-out |  | Ahmed Marhoon | As a minimum, vendor to supply documents listed under VENDOR DRAWINGS AND DATA REQUIREMENTS of the BMPS Volume 3. TTSJV to cross check with the relevant BMPS (in this case BMPS-C-50114) and ensure compliance with the referenced section and/or highlight deviations, if any. Typical comment | Agreed. The documents herein (000-C-SOW-70007-001) indicated are as per requested in the document BMPS-C-50114; as long as they apply.
6 | Callout |  | Mohamed Ayyash | commissioning | Agreed. This will be corrected and updated in next emission.
7 | Callout |  | Mohamed Ayyash | this is 2HCU reactors not columns | Agreed. This will be corrected and updated in next emission.
8 | Text Box |  | Hasan Asad
9 | Text Box |  | Hasan Asad | Add: Complete LCCA study | We've understood that this type of analysis neither applies nor it is into the scope of pressure vessels.
10 | Callout |  | Mohamed Ayyash | this is 2HCU reactors not columns | Agreed. This will be corrected and updated in next emission.