## 000-E-ITP-70007-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 4 | Yousif Ahmadi | Add "R" for tube expansion inspection for level 3
2 | Callout | 3 | Yousif Ahmadi | Add in Type: "Tube bundle and headers"
3 | Callout | 2 | Yousif Ahmadi | Add pre-Shipping section
4 | Callout | 3 | Yousif Ahmadi | Change to 3.2 for level 2 inspection
5 | Callout | 1 | Yousif Ahmadi | Check and correct the equipment numbers 0190013
6 | Callout | 1 | Yousif Ahmadi | Check and correct the equipment numbers 019E0008, 0190012
7 | Text Box | 2 | Ahmed Marhoon | Inspection and Test Plan to include the participation of the client in accordance with the BMP agreed procedures. Loop testing plan to be detailed. Tests related to instrumentation, control and safety to comply with the BMPS J series specifications/instructions. As a minimum, the relevant Checklist as agreed for the BMP shall be referenced in the ITP.
8 | Call-out | 1 | Ahmed Marhoon | There is inconsistency in quoting the name of the Contractor. Both Tecnicas Reunidas S.A and Technip Italy have been stated in this document. Contractor to regularize.