## 000-E-SOW-70007-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 3 | Mahdi Ali | 3D Model??
2 | Callout | 6 | Yousif Ahmadi | ADD: Equipment initial UT gauging reports
3 | Call-out | 4 | Ebrahim | and VFD
4 | Cloud+ | 2 | A.Jabbar Mahmood | Correct the equipment numbers as per the new numbering 019E0008, 019E0012, 019E0013.
5 | Text Box | 5 | Ebrahim | Electric motor and VFD asset sheets before delivery
6 | Typewritten Text | 1 | Mohamed Ayyash | General Comment Throughout the short term for the word "drawings" has been written in different none standard forms. Need to be consistent and for better representation write the full word.
7 | Call-out | 2 | 986131 | Is 010E0023 not part of this MR - please check and correct as appropriate.
8 | Cloud+ | 2 | Mohamed Ayyash | Page 2/6 in EQUIPMENT/MATERIAL SUPPLY table item 5 should read "Commissioning and Start-up" and not vise versa.
9 | Cloud+ | 5 | Mohamed Ayyash | Page 5/6 item A5015 should read "Commissioning and Start-up" and not vise versa.
10 | Call-out | 4 | Ahmed Marhoon | Supplier to comply with all the applicable BMPSs and provide, as a minimum, all the documents, hardware, software and services according to the relevant sections of the BMPSs in the agreed standard formats of the project. List to reflect all the required deliverables in accordance to BMPS.