## 000-F-GRD-60001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | add document title in the header
2 | Call-out | Page 1 | Rashed Almudahka | confirm unit no.
3 | Call-out | Page 1 | Mahdi Ali | Unit number shall always be 3 digits, i.e. 018
4 | Text Box | Page 1 | rob.urban | The pro's and con's of having a combined convection section for the reactor feed furnace and recycle hydrogen furnace need to be discussed and evaluated first before this can be considered as an option. Also input from CLG is required. The option is on Hold in the MR but bidders should not pay attention to this until this option has been properly evaluated and approved
5 | Call-out | Page 4 | Hasan Al Noaimi | Hydrocracking
6 | Call-out | Page 4 | Hasan Al Noaimi | 1
7 | Text Box | Page 4 | Mahdi Ali | Reference shall be made to Bapco document number
8 | Call-out | Page 6 | Ali Abbas | Including sequence flow charts per typical BMPS drawings.
9 | Call-out | Page 6 | Ali Abbas | Cause and Effect and lowchart as per typical BMPS drawing.
10 | Call-out | Page 6 | Ali Abbas | Note: 4" Nozzle requirement for CEMS/PEMS to be also covered were applicable with access ladder/platform. Location to be finalized with PEMS/CEMS vendor.
11 | Call-out | Page 9 | Hasan Al Noaimi | ESD setting
12 | Call-out | Page 9 | Ali Abbas | Include CHAZOP support if required.
13 | Call-out | Page 9 | Rashed Almudahka | Para 3.2.3.2.
14 | Call-out | Page 9 | Rashed Almudahka | Supplier shall comply to requested documents as per BMPS-J6 specifications
15 | Call-out | Page 9 | Rashed Almudahka | electrical drawings as per BMPS-P3
16 | Call-out | Page 10 | Ali Abbas | Refer to BMPS for Instrumentation certification requirements.
17 | Call-out | Page 13 | Rashed Almudahka | para 3.6.
18 | Call-out | Page 14 | Rashed Almudahka | as per BMPS-F1
19 | Call-out | Page 14 | Ali Hasan | Pilot ignition, detection and integration with the heater BMS to be included in the Scope of Supply, and narrative for the control/firing sequence to be provided.
20 | Call-out | Page 14 | Ali Hasan | Pilot detector sensor, using ionization rod or flame eye, shall be included in the Scope of Supply. Both detection type shall be evaluated during the design review.
21 | Call-out | Page 15 | Hasan Al Noaimi | combostibles
22 | Call-out | Page 15 | Ali Abbas | Minor correction: Combustible per Cell/Bank
23 | Call-out | Page 15 | Ali Abbas | Smart as per BMPS Spec
24 | Call-out | Page 15 | Ali Abbas | Please note the followings: 1. For ESD Trip, Pull Buttons to be specified with voting per applicable BMPS Spec. 2. IS and non-IS to be segregated in the local panel. 3. Local panel faults e.g. power failure, common alarms etc. to be provided and connected to DCS for operator alert.
25 | Text Box | Page 16 | Hasan Asad | At least add. set to cater for emergencies during PRE-COMM & COMM.
26 | Call-out | Page 18 | Ali Abbas | Include Owner for below activities
27 | Call-out | Page 18 | Ali Abbas | Include CHAZOP
28 | Call-out | Page 20 | Ali Abbas | General comment: Reference shall be made to BMPS spec and std drawings and AVL
29 | Call-out | Page 22 | Ali Abbas | Access shall be provided for PEMS/CEMS Nozzle.
30 | Call-out | Page 23 | Rashed Almudahka | purchaser
31 | Text Box | Page 23 | Mahdi Ali | Follow Bapco numbering system
32 | Text Box | Page 24 | Mahdi Ali | A1
33 | Text Box | Page 26 | Ahmed Bucheeri | Provide updated plot plan with new equipment number
34 | Call-out | Page 26 | Ravi Kumar | Please add in 5.3.1: State this is a preliminary plot plan
35 | Text Box | Page 27 | rob.urban | 018F1001/1002 and 018F2001/2002 can also have a common stack
36 | Text Box | Page 29 | Hasan Asad | Detailed Maintenance Consideration report shall be provided which serves detailed T&I list of activities and required spare parts.
37 | Call-out | Page 30 | Ebrahim | in accordance with BMPS-P1 and BMPS-A1.
38 | Text Box | Page 31 | Mahdi Ali | add space
39 | Text Box | Page 34 | Hasan Asad | Spare parts list shall include first run list of spares and consumables.
40 | Text Box | Page 34 | Hasan Asad | Capital spares shall be delivered with preservation strategy.
41 | Call-out | Page 34 | Rashed Almudahka | shall