## 000-F-ITP-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ahmed Marhoon | Inspection and Test Plan to include the participation of the client in accordance with the BMP agreed procedures. Loop testing plan to be detailed. Tests related to instrumentation, control and safety to comply with the BMPS J series specifications/instructions. As a minimum, the relevant Checklist as agreed for the BMP shall be referenced in the ITP.
2 | Text Box | 2 | Ebrahim | High
3 | Callout | 2 | Yousif Ahmadi | Add Pre-shipping inspection Section
4 | Callout | 2 | Yousif Ahmadi | Add: Quality control manufacturing Dossier to all Documentation of next pages
5 | Call-out | 3 | Ahmed Bucheeri | Before and
6 | Callout | 3 | Yousif Ahmadi | PWHT, THS, NDE... Procedures "R"
7 | Callout | 3 | Yousif Ahmadi | Add: During Fabrication
8 | Callout | 3 | Yousif Ahmadi | Forming "R"
9 | Callout | 3 | Yousif Ahmadi | Production Weld Coupons "W"
10 | Text Box | 7 | Ahmed Bucheeri | PMI for alloyes
11 | Call-out | 8 | Ahmed Bucheeri | Percentage will be higher basis welding process. Mention the process
12 | Text Box | 8 | Ahmed Bucheeri | WPS & PQR to be provided for reviewing
13 | Text Box | 8 | Ahmed Bucheeri | PMI for anchors
14 | Text Box | 9 | Ahmed Bucheeri | WPS & PQR to be provided for reviewing
15 | Text Box | 11 | Sankara | High : Typical