## 000-F-MRQ-80002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp |  | Nalini Mohan
2 | Text Box |  | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
3 | Arrow |  | Jeung.Kim
4 | Text Box |  | Jeung.Kim | What is AP?
5 | Arrow |  | Jeung.Kim
6 | Text Box |  | Jeung.Kim | Typical comment: All data sheets have to be updated according to FEED validation and detail design development and all such updating has to be incorporated in the purchase order.
7 | Callout |  | Nalini Mohan | Add Fire Exposed Envelope and Fireproofing Limits drawings
8 | Rectangle |  | Nalini Mohan
9 | Callout |  | Nalini Mohan | Incorporate FEED drawings as part of initial MR with a note stating that these will be developed in due course and vendor will be informed
10 | Callout |  | Nalini Mohan | Include AVL along with first issue of MR release instead of noting as TBD