## 000-F-SOW-80001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp |  | Nalini Mohan
2 | Text Box |  | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3
3 | Cloud |  | Edgardo
4 | Cloud |  | Edgardo
5 | Call-out |  | Edgardo | Please confirm unit number
6 | Text Box |  | Jeung.Kim | Does the vendor provide the 3D model?
7 | Arrow |  | Jeung.Kim
8 | Callout |  | Mohamed Ayyash | align
9 | Arrow |  | Mohamed Ayyash
10 | Callout |  | Mohamed Ayyash | align
11 | Arrow |  | Mohamed Ayyash
12 | Callout |  | Mohamed Ayyash | align
13 | Arrow |  | Mohamed Ayyash
14 | Call-out |  | Ahmed Marhoon | List of Hardware, Software and Services to be updated capturing all the requirements covered under BMPS-J series specifications such as J2, J3, J6 ...etc. Format of deliverables to as amply with the project agreed specs.
15 | Callout |  | Mohamed Ayyash | align
16 | Arrow |  | Mohamed Ayyash
17 | Callout |  | Mohamed Ayyash | align
18 | Arrow |  | Mohamed Ayyash