## 000-G-GRD-70004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Isamu | Please list here all tag numbers and service name as with other MR for immediate identification of equipment
2 | Text Box | 1 | Isamu | Owner is very unable to consider issuing MR for inquiry for equipment of which the data sheets are pending and not completed. As the data sheet contain the bulk of technical mech and process information, Owner request that this MR be resubmitted with completed documents (data sheet).
3 | Text Box | 1 | Isamu | BB1 & BB2 are very comparable (in fact same except radially and axially split only (respectively). BB3 is by far different multi-stage pump for much higher pressure and may emply pressurized lube system and many other supporting accessories. Owner strongly asks to separate the MR for BB3 type equipment if already specified as BB3 in FEED data sheet,
4 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets.
5 | Text Box | 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
6 | Text Box | 2 | Sankara | Please correct the index.
7 | Text Box | 3 | Isamu | This entire para is not applicable and no priorities to be listed. Please refer to BMPS-A2-II & BMPS-G2-II
8 | Callout | 4 | Isamu | Insert " When specified and indicated on data sheet"
9 | Callout | 5 | Isamu | Insert " When specified and indicated on data sheet"
10 | Text Box | 7 | Hasan Asad | General Comments: 1.Instrument for pump vibration and bearing temperature shall be as per Machinery Monitoring Instrument Table (doc. No. 2520-z000-NM-1515-03-A) and Contractor rotating equipment criticality assessment results. 2.The Owner preference is to select John Crane for the wet mechanical seal application together with the API sealing systems and filtration to maximize the standardization with the existing base business and for inventory interchangeability. Although Flowserve is also in the AVL, they should fully satisfy the additional requirement as stated in the AVL document notes REQUIREMENTS OF LCCA AND FOR BEING ABLE TO BE PROVIDE LONGTERM SERVICE POST-PROJECT THROUGH LOCAL SERVICE / TESTING CENTRE AND WAREHOUSE IN BAHRAIN . 3.Mechanical seal selection shall be in accordance to Seal OEM/Vendor selection chart and High Consequence Pump criteria as specified in BMPS G9 shall be considered as well. 4.Bearing life shall be calculated and provided. 5.Complete unit test requirement shall be selected on case by case basis. 6.The seal API plan shall be accessible and a filling cart is provided for filling the seal pot. 7.Close clearance metalized throat bushing for optimal control of stuffing box pressure (Pump Vendor to advice). 8.If the pump and motor to be connected to oil mist system, labyrinth bearing housing isolators shall be used. 9.General purpose steam turbine to API 611 shall be equipped with mechanical over speed trip mechanism in addition to the electronic. 10. If a different media to be used for pump start-up, the seal design should be applicable.
11 | Callout | 7 | Adnan Alothman | For all critical equipment, company representative attendance is required as per BMPS-B11.
12 | Call-out | 8 | Ahmed Marhoon | What about HAZOP/SIL/CHAZOP?
13 | Call-out | 8 | Ahmed Marhoon | Replace with IFAT
14 | Cloud+ | 8 | Ahmed Marhoon | These activities are major milestones for the package and it is mandatory to be attended by Client representatives. Attendees list to be updated based on the agreed project responsibility matrix.
15 | Call-out | 8 | Ahmed Marhoon | The way the exclusion list is stated in this document results in misunderstandings and leads to unclear SOW. For example, Warm-Up line is excluded from the supplier SOW. Requirement and design of the warm-up lines are normally a joint responsibility between the contractor and supplier and hence it cannot be excluded from the supplier SOW. A comprehensive list of exclusions to be developed by the contractor and attached to the MR for better clarity. This is a typical comment for all MRs.
16 | Callout | 16 | Mohamed Ayyash | Should read "Commissioning and Start-up" not vice versa.
17 | Callout | 16 | Mohamed Ayyash | Add "Commissioning" to the sentance
18 | Callout | 17 | Mohamed Ayyash | Add space between the two paragraphs
19 | Callout | 17 | Mohamed Ayyash | Is the Commissioning phase included ?
20 | Text Box | 18 | Ahmed Marhoon | The following are comments related to instrumentation and control. Contractor is requested to update the other documents issued as part of this transmittal based on the comments stated herein and ensure consistency prior to release of MR to suppliers. 1. Add a clear note on Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added. 2. Instruct the supplier to source instrumentations from project AVL only. 3. Add a note to the supplier with reference to the applicable BMPS to design and supply the system according to the final PID. Functional design specifications covered in this MR shall be firmed based on the approved PID. Vendors to be clearly notified on the necessity to include all the Hazop3/SIL recommendations and changes made Post-EPC-Development. 4. Minimum Flow arrangement/design shall be reviewed and confirmed by the supplier. Contractor to consider the pumps protection and process requirements according to manufacturer and licensor recommendations. 5. Where applicable, supplier to be notified on consideration of ESD interlock and Permissive signals requirements per the PID. 6. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 7. All the BN machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 8. Narrative/flow charts/cause and effect, in Client standard formats, shall be provided for any control or sequence logic. 9. Scope of supply for the interposing relays to be clearly defined. 10. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting &etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 11. In addition to BMPS-J6 and J2, all applicable BMPS from J class to be added for the supplier to comply with. e.g. J3, J15 ... etc. To emphasize and where applicable, BMPS-J16 to be referenced for anti-surge system and BMPS-J18 to be referenced for turbine Speed Governor for the supplier to comply with. All instruments and control systems to be designed according to BMPS specifications. 12. Supplier to be instructed to generate all instrument data sheets, hook ups ...etc. in project specs (according to Bapco standard formats) and to be developed in SPI format. Typical formats can be provided to the supplier at a later stage for compliance. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 13. Where applicable, compliance to licensor mandatory and recommended requirements to be included. 14. Contractor is requested to validate the models quoted for the instrumentation and ensure that the latest models are supplied for BMP in accordance to the projects specifications. To avoid supplying an obsolete and/or products at their obsolescence phase, vendors to be instructed to provide Products Life-Cycles/Road-maps. For example, model YTA310 for ESD Transmitter has recently announced obsolete and needs to be replaced with the latest model number. This is a general comment that need to be globally addressed by the contractor. 15. Peak 150 has been specified for the Governor based on the model number mentioned on the BMPS-K5. However, with the Woodward latest model Peak200 available in the market which is replacing Peak150, will Peak150 still be supported and not going to be at the end of its life-cycle by the end of the project? TTSJV to verify with the supplier and advise the client for review and approval. Typical comment. 16. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.
21 | Text Box | 19 | Mahdi Ali | Change the orientation of this page.