## 000-G-ITP-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) on all pages
2 | Callout | 2 | bapco-user | Include Pre-shipping inspection Section
3 | Callout | 2 | bapco-user | Add to before fabrication: WPS/PQR "R"
4 | Callout | 2 | bapco-user | Add to before fabrication: Welders and N.D.E. Operators "R"
5 | Text Box | 2 | Hasan Asad | Complete Unit Test
6 | Text Box | 2 | Hasan Asad | W
7 | Cloud+ | 5 | bapco-user | Reservoirs and coolers: NDE & PMI change to W
8 | Cloud+ | 11 | bapco-user | Filters, Small vessels, Coolers, Etc: Change NDE & PMI from R to W
9 | Callout | 12 | bapco-user | Lube oil pumps: Add Painting Check
10 | Callout | 12 | bapco-user | W for Painting Cehck
11 | Cloud+ | 13 | bapco-user | Baseplate: change NDE to W