## 000-G-MRQ-70004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Isamu | Owner is strongly unable to consider issuing MR for inquiry for equipment of which the data sheets are pending and not completed. As the data sheet contains the bulk of technical mech and process information, Owner request that this MR be resubmitted with completed documents (data sheet).
2 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets.
3 | Callout | 1 | Mohamed Ayyash | Include pumps service
4 | Text Box | 2 | A.Jabbar Mahmood | TR to provide all the remaining datasheets for owner review.
5 | Call-out | 5 | Mahdi Ali | Remove suffix in unit number
6 | Text Box | 6 | A.Jabbar Mahmood | Any applicable Licensor Specifications or Drawings shall be included