## 000-H-GRD-60001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 6 | Omran A | & BAPCO Rep
2 | Text Box | 15 | Omran A | & maintenance
3 | Call-out | 10 | Ebrahim | As electrical is not applicable, approved electrical equipment list shall be removed from MRQ
4 | Text Box | 14 | Omran A | as per BMPS-S12 "Guidelines for preparations of spare parts"
5 | Call-out | 15 | Ali Abbas | engineering
6 | Call-out | 10 | Ali Abbas | insure all other applicable BMPS-J series specifications, standard and typical drawings are also included. Also, for nozzle connections to be on hold until instrumentation types are finalized.
7 | Callout | 3 | Bernard.Grace | It shall be the Contractors (and Suppliers / Subcontractors) responsibility to bring all conflicts and deviations to the Owners attention in a timely manner and request a ruling interpretation or a resolution in writing. Refer to Project Specification No. BMPS-A2 (Specifications, Codes and Standards) for guidelines on how to manage conflicts and deviations
8 | Text Box | 10 | Ahmed Habib | Refer to BMPS-J14_0