## 000-H-ITP-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | bapco-user | MR code number is 000-H-MRQ-70001-001
2 | Callout | 1 | bapco-user | Change all Tecnicas Reunidas to CONTRACTOR in this page
3 | Text Box | 2 | Mahdi Ali | Always reference Bapco number
4 | Callout | 2 | bapco-user | Add WPS/PQR/Weld Map with "R"
5 | Callout | 2 | bapco-user | Change painting to "W"
6 | Callout | 2 | bapco-user | Add Pre-shipping inspection section
7 | Call-out | 2 | 986131 | Ejector performance test
8 | Text Box | 3 | Mahdi Ali | Always reference Bapco number
9 | Text Box | 3 | Mahdi Ali | Always reference Bapco number
10 | Callout | 3 | bapco-user | Change painting to "W"
11 | Call-out | 3 | 986131 | Ejector performance test
12 | Text Box | 4 | Mahdi Ali | Always reference Bapco number
13 | Text Box | 4 | Mahdi Ali | Always reference Bapco number
14 | Callout | 4 | bapco-user | Change painting to "W"
15 | Call-out | 4 | 986131 | Ejector performance test