## 000-H-SOW-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Correct page numbers. Should be 1/5, 2/5....etc | Noted and corrected in next revision.
2 | Text Box | 2 | Mahdi Ali | Unit number shall be of 3 digits | Noted and corrected in next revision.
3 | Callout | 3 | Mohamed Ayyash | adjust column width to read full word (this applies to all pages) | Noted and corrected in next revision.
4 | Text Box | 4 | Mahdi Ali | drawings | Noted and corrected in next revision.
5 | Text Box | 5 | Ahmed Marhoon | The above list seems incomplete. Documents like Narrative/flow charts/cause and effect shall be also provided for any control or sequence logic. Contractor to update the above list based on the list of deliverables covered in BMPS specifications such as BMPS-J6. | Noted and included in next revision.