## 000-K-GRD-70002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Gmarini | AP
2 | Text Box | 1 | Gmarini | AP
3 | Text Box | 1 | Gmarini | ISSUE FOR INQUIRY - PENDING
4 | Text Box | 1 | Adnan Alothman | Data sheets for the Compressor & Turbine are not available for review.
5 | Text Box | 1 | Mahdi Ali | Add equipment number
6 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
7 | Text Box | 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractor’s request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
8 | Call-out | 3 | Ahmed Marhoon | Licensor's mandatory technical requirements to be met.
9 | Callout | 3 | Adnan Alothman | As per the Contract, Annex1-Technical documents do not have any order of precedence. Please correct this to align with EPC Contract.
10 | Text Box | 4 | Hasan Asad | The Suuplier/Vendor shall provide complete LCCA report for the main unit and the associated systems.
11 | Call-out | 5 | Ahmed Marhoon | Add CHAZOP
12 | Call-out | 5 | A.Jabbar Mahmood | What about owner representative?
13 | Cloud+ | 5 | Ahmed Marhoon | These activities are considered major milestones for this system and shall be attended by owner's representatives. List to be updated according to the project's agreed responsibility matrix.
14 | Callout | 5 | Adnan Alothman | For all critical equipment, company representative attendance is required as per BMPS-B11.
15 | Call-out | 5 | Ahmed Marhoon | What about ESD?
16 | Call-out | 5 | Ahmed Marhoon | Replace FAT with IFAT. Also, what about SAT?
17 | Text Box | 6 | Hasan Asad | Radial and Axial vibration probes shall be 3 (not 2) to have 2oo3 voting system.
18 | Text Box | 6 | Hasan Asad | Axial displacement shall be 3 probes (not 3) to have 2oo3 voting system.
19 | Cloud | 6 | Hasan Asad
20 | Call-out | 6 | Sameer Foujdar | Vendor to confirm it should be air ejector or steam ejector for gland condenser.
21 | Text Box | 7 | Hasan Asad | System cleaning and flushing shall be under Vendor/Supplier supervision and satisfaction.
22 | Call-out | 7 | Sameer Foujdar | To consider having a lube oil centrifuge system for the lube oil reservoir.
23 | Call-out | 7 | Sameer Foujdar | Lube oil accumulator on the pump discharge to be considered.
24 | Text Box | 8 | Hasan Asad | Field erection and installation shall be under Vendor/Supplier supervision and satisfaction.
25 | Text Box | 11 | Hasan Asad | Probes shall be installed by the Vendor/Supplier at fabrication shop.
26 | Call-out | 11 | Sameer Foujdar | Electronics and logic for startup should also be provided.
27 | Text Box | 16 | Ahmed Marhoon | The following are comments related to instrumentation and control. Contractor is requested to update the other documents issued as part of this transmittal, in addition to the data sheet, based on the comments stated herein and ensure consistency prior to release of MR to suppliers. 1. Add a clear note on Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added. Also, in addition to BMPS-J6, all applicable BMPS-J series to be referenced (such as J2, J3, J31 …etc) for the supplier to comply with. 2. Instruct the supplier to source instrumentations from project AVL only. 3. Add a note to the supplier with reference to the applicable BMPS to design and supply the system according to the final PID. Functional design specifications covered in this MR shall be firmed based on the approved PID. Vendors to be clearly notified on the necessity to include all the Hazop3/SIL recommendations and changes made Post-EPC-Development. 4. Anti-Surge design shall be reviewed and confirmed with the supplier. Contractor to consider the compressors protection and process requirements according to manufacturer and licensor recommendations. Supplier to be instructed to comply with the relevant BMPS-K specifications and BMPS-J16 and BMPS-J18 in addition to the general instrumentation specifications. 5. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 6. All the machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 7. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 8. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 9. Supplier to be instructed to generate all instrument data sheets, hook ups ...etc. in project specs (according to Bapco standard formats) and to be developed in SPI format. Typical formats can be provided to the supplier at a later stage for compliance. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 10. Compliance to licensor's mandatory and recommended requirements to be included. 11. Supplier to comply with all the applicable BMPSs and provide, as a minimum, all the documents, hardware, software and services according to the relevant sections of the BMPSs in the agreed standard formats of the project. List to reflect all the required deliverables in accordance to BMPS. 12. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.
28 | Text Box | 18 | Hasan Asad | The spare rotors shall be service test by the Vendor/Supplier during the FAT and shall be stored in a N2 pressurized steel canister.