## 000-K-ITP-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
2 | Callout | 1 | Mohamed Ayyash | What is 000M? should be 7CDU/2HCU
3 | Text Box | 1 | Ahmed Marhoon | Inspection and Test Plan to include the participation of the client in accordance with the BMP agreed procedures. Loop testing plan to be detailed. Tests related to instrumentation, control and safety to comply with the BMPS J series specifications/instructions. As a minimum, the relevant Checklist as agreed for the BMP shall be referenced in the ITP. For example, BMPS-K-50409 is applicable for the Reciprocating Compressors. This is a typical comment for all ITPs.
4 | Callout | 2 | Mohamed Ayyash | Complete line
5 | Text Box | 2 | Hasan Asad | The Compressor Complete unit commissioning shall be supervised by Vendor/Supplier.
6 | Callout | 2 | Mohamed Ayyash | Correct
7 | Callout | 2 | Yousif Ahmadi | Add Pre-shipping inspection
8 | Cloud+ | 3 | Yousif Ahmadi | Add "R" against following WPS/PQR ...... Inspection procedures ... Welding consumable ...
9 | Callout | 19 | Mohamed Ayyash | Overlap with line (Correct)