## 000-K-SOW-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets | Not aplicable. This is not a typo mistake | N
2 | Callout | 1 | Mohamed Ayyash | What is 000M? should be 7CDU/2HCU | This is not applicable. This is a generic designation of the document assigned by TTSJV DCC and cannot be modified. | N
3 | Call-out | 2 | Raj | This list to include all Capital Spares required for the equipment as per the Contract Annex 1 | This comment does not apply. In contract Annex 1, capital spare parts for reciprocating compressors are not listed, therefore, they are not included in Contractor/Vendor's scope of supply. | N
4 | Call-out | 2 | Mahdi Ali | Motor equipment code is 'M' and not 'KM' | Noted, to be modified and updated in following document revision | Y
5 | Call-out | 2 | Raj | Change the motor tags as per the agreed equipment numbering | Noted, to be modified and updated in following document revision | Y
6 | Call-out | 3 | Sameer Foujdar | Supplier shall provide startup procedure along with logic sequence and pre startup requisites. | Document installation, commisioning and start-up manuals (A5015) is already requested IN VDDR and it will be provided by vendor during Engineering phase. | N
7 | Callout | 4 | Mohamed Ayyash | Typo | Noted, to be modified and updated in following document revision | Y
8 | Call-out | 5 | Ahmed Marhoon | Supplier to comply with all the applicable BMPSs and provide, as a minimum, all the documents, hardware, software and services according to the relevant sections of the BMPSs in the agreed standard formats of the project. List to reflect all the required deliverables in accordance to relevant BMPS J series specifications. | SOW document reflecs all applicable documents to reciprocating compressor package to be supplied by manufacturer during Engineering detailed phase, according to BMPS specifications. | N
9 | Callout | 5 | Mohamed Ayyash | better to write full words | Names of the document shall be as per system. They cannot be modified | N
10 | Callout | 6 | Mohamed Ayyash | Should read Commissioning and Start-up ( not vise versa) | Noted, to be modified and updated in following document revision | Y
11 | Text Box | 6 | Hasan Asad | Including troubleshooting guideline for complete unit and associated systems. | Document Operation and maintenance manuals (A5016) is already requested on VDDR and it will be provided by vendor during Engineering phase. | N
12 | Text Box | 8 | A.Jabbar Mahmood | Ensure that all performance curves requested in the equipment datasheets are included. | Noted, all applicable performance curves for compressor package are already requested in SOW document. | N