## 000-K-SOW-70002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box |  | Gmarini | AP
2 | Text Box |  | Gmarini | AP
3 | Text Box |  | Gmarini | ISSUE FOR INQUIRY - PENDING
4 | Text Box |  | Mahdi Ali | Add equipment number
5 | Cloud+ |  | Mohamed Ayyash | Be consistent, write the word "Eqpt" in full
6 | Cloud+ |  | Mohamed Ayyash | Be consistent, write the word "Eqpt" in full i.e. Equipment
7 | Cloud+ |  | Mohamed Ayyash | Be consistent, write the word "Eqpt" in full i.e. Equipment
8 | Call-out |  | Ahmed Marhoon | Supplier to comply with all the applicable BMPSs and provide, as a minimum, all the documents, hardware, software and services according to the relevant sections of the BMPSs in the agreed standard formats of the project. List to reflect all the required deliverables in accordance to BMPS J series.
9 | Cloud+ |  | Mohamed Ayyash | Be consistent, write the word "arr.nt" in full i.e arrangement
10 | Cloud+ |  | Mohamed Ayyash | None standard writting. Use full wording.
11 | Cloud+ |  | Mohamed Ayyash | Hidden texts, need to correct
12 | Cloud+ |  | Mohamed Ayyash | None standard writting. Use full wording.
13 | Callout |  | Mohamed Ayyash | Should read "Commissioning and Start-up" not vice versa.
14 | Text Box |  | A.Jabbar Mahmood | Ensure that all performance curves requested in the equipment datasheets are included.
15 | Text Box |  | Hasan Asad | The Vendor/Supplier shall provide LCCA report for 20 years for complete unit and the associated systems.