## 000-S-GRD-70003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
2 | Cloud+ | 1 | Mohamed Ayyash | General Comment: Add zero to unit number throughout the document. should read 019
3 | Callout | 1 | Mohamed Ayyash | Add Unit name '2HCU"
4 | Text Box | 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
5 | Text Box | 2 | Mahdi Ali | add document title in the header
6 | Callout | 3 | bapco-user | As per the Contract, Annex1-Technical documents do not have any order of precedence. Please correct this to align with EPC Contract.
7 | Callout | 4 | Robert.Kawitzki | Vents
8 | Call-out | 4 | Ali Abbas | with local panel for specific local control/status indication as requited. To be finalized during design review.
9 | Text Box | 6 | Mahdi Ali | s
10 | Cloud+ | 6 | Ahmed Marhoon | These activities are considered main milestones for the package and need to be attended by the client. List to be updated based on the agreed responsibility matrix of the project.
11 | Call-out | 6 | Ahmed Marhoon | Add IFAT
12 | Call-out | 6 | Ahmed Marhoon | What about Hazop/SIL and CHAZOP?
13 | Call-out | 6 | Ahmed Marhoon | Will it be only one model for the EPC phase? The actual requirements and details of the 3D model (30%, 60%, 90%) to be clarified.
14 | Call-out | 6 | Ahmed Marhoon | SAT and training are not covered in the Meeting programs table. To be listed. Typical comment for all packages where suppliers involvement is required during installation, pre-commissioning, commissioning and training activities.
15 | Callout | 6 | bapco-user | For all critical equipment, company representative attendance is required as per BMPS-B11.
16 | Text Box | 7 | Sankara | Specify the right Gas Groups
17 | Call-out | 7 | Ahmed Marhoon | What about equipment requiring fireproofing per the FEE classification and being supplied by vendor? This is a general concern for all packages and need to be clarified by the TTSJV.
18 | Text Box | 10 | Sankara | If electric motors are required, include the vendor data requirements and inspection checklists in the scope of supply.
19 | Text Box | 18 | Hasan Asad | Vendor to provide LCCA report.
20 | Text Box | 18 | Ahmed Marhoon | The following are comments related to instrumentation and control. Contractor is requested to update the other documents issued as part of this transmittal, in addition to the data sheet, based on the comments stated herein and ensure consistency prior to release of MR to suppliers. 1. All applicable BMPS-J series to be referenced (such as J3, J31 &etc) for the supplier to comply with. 2. Instruct the supplier to source instrumentations from project AVL only. 3. Add a note to the supplier with reference to the applicable BMPS to design and supply the system according to the final PID. Functional design specifications covered in this MR shall be firmed based on the approved PID. Vendors to be clearly notified on the necessity to include all the Hazop3/SIL recommendations and changes made Post-EPC-Development. 4. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 5. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting &etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 6. Supplier to be instructed to generate all instrument data sheets, hook ups ...etc. in project specs (according to Bapco standard formats) and to be developed in SPI format. Typical formats can be provided to the supplier at a later stage for compliance. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 7. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval. 8. Contractor is requested to validate the models quoted for the instrumentation and ensure that the latest models are supplied for BMP in accordance to the projects specifications. To avoid supplying an obsolete and/or products at their obsolescence phase, vendors to be instructed to provide Products Life-Cycles/Road-maps. For example, model YTA310 for ESD Transmitter has recently announced obsolete and needs to be replaced with the latest model number. This is a general comment that need to be globally addressed by the contractor.