## 000-S-GRD-80002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box |  | Sameer.Ahmed
2 | Callout |  | Sameer.Ahmed | No. 6, 7 & 8 DESALINATION PLANTS
3 | Stamp |  | Nalini Mohan
4 | Text Box |  | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3
5 | Text Box |  | Jeung.Kim | Does this specification is part of MR or separate deliverable? Please note IPMT only reviewed the MR and MDS according to Contractor request during KOM.- typical comment
6 | Callout |  | Mohamed Ayyash | Correct: Commissioning and Start up (not vise versa)
7 | Callout |  | Mohamed Ayyash | space
8 | Cloud+ |  | Ahmed Marhoon | The term COMPANY was not defined.
9 | Arrow |  | Mohamed Ayyash
10 | Callout |  | Mohamed Ayyash | pre commissioning,
11 | Cloud+ |  | Sameer.Ahmed | Remove N and just keep 3
12 | Call-out |  | Ahmed Marhoon | Add to the supplier's SOW: Assistance and involvement of the vendor during CHAZOP workshop and study if required.
13 | Cloud+ |  | Ahmed Marhoon | Supplier needs to participate in Hazop as and when required. Also add SIL, if required.
14 | Call-out |  | Ahmed Marhoon | Add: Integrated Factory Acceptance Test (IFAT). Also add ESD FAT, if applicable.
15 | Cloud+ |  | Ahmed Marhoon | Participants shall be according to the BMP's agreed responsibility matrix/plan. Some of the milestones must be attended by Bapco's IPMT personnel. These activities need to be clearly highlighted.
16 | Callout |  | Mohamed Ayyash | Why the numbers are ouside the table ?
17 | Arrow |  | Mohamed Ayyash
18 | Arrow |  | Mohamed Ayyash
19 | Callout |  | Mohamed Ayyash | delete ; from all
20 | Arrow |  | Mohamed Ayyash
21 | Arrow |  | Mohamed Ayyash
22 | Call-out |  | Ahmed Marhoon | All instrumentation shall comply with the BMPS-J series (such as J6) and general BMPS (such as A3) specifications. All relevant BMPSs shall be reference in this document and supplied to the vendor. All the documents submitted as part of this transmittal shall be updated accordingly.
23 | Call-out |  | Ali Abbas | In addition to BMPS-J series, all standard and typical instrumentation drawings to be issued to vendor/supplier to follow.
24 | Call-out |  | Ali Abbas | Vendor to note signal type segregation requirement for junction boxes.
25 | Callout |  | Mohamed Ayyash | Add comma ,
26 | Callout |  | Mohamed Ayyash | Move to next page
27 | Callout |  | Sameer.Ahmed | Supplier shall submit the proposed sub-supplier list for the equipment materials along with the proposal.
28 | Call-out |  | Ahmed Marhoon | Add the relevant BMPS-J series specifications and instruct the suppliers to meet all the requirements. The listed items are general in nature and do not cover all the requirements specified in BMPS.
29 | Call-out |  | Ahmed Marhoon | Add all the relevant BMPS-J series specifications such as J3, J7 ...etc.
30 | Call-out |  | Ahmed Marhoon | Add a note on possibility for considering some non-critical instruments as wireless based on the criteria being developed for BMP. Also add BMPS-J10 for reference.
31 | Call-out |  | Ahmed Marhoon | Add a note for the vendor to supply instruments only from the approved AVL.
32 | Line |  | Mohamed Ayyash
33 | Typewritten Text |  | Mohamed Ayyash | Units
34 | Cloud+ |  | Sameer.Ahmed | Include the source of the basis of this nozzle allowable load
35 | Typewritten Text |  | Mohamed Ayyash | S
36 | Arrow |  | Mohamed Ayyash
37 | Callout |  | Mohamed Ayyash | Use capital S
38 | Callout |  | Mohamed Ayyash | Correct: It is Commissioning and Start up ( not vise versa)
39 | Callout |  | Mohamed Ayyash | , commissioning
40 | Callout |  | Mohamed Ayyash | space
41 | Callout |  | Mohamed Ayyash | , Start up