## 000-S-GRD-80003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractor’s request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3
2 | Callout | 1 | balagangadhar.k | Match date format, typ. for all documents
3 | Text Box | 1 | Mahdi Ali | add title of the document in the header
| Stamp | 1 | Nalini Mohan
4 | Callout | 1 | Julio.Aguilar | Package tag number to be included.
5 | Callout | 1 | Isamu | No comment
6 | Text Box | 3 | Nalini Mohan | Documents priority to be deleted
7 | Callout | 4 | Salman Jaffer | Please refer to Exhibit F for requirement for training.
8 | Text Box | 5 | Hasan Asad | Owner Operation and Maintenance shall be involved in these meeting basis need.
9 | Text Box | 5 | Nalini Mohan | Company considers Supplier is required to submit the SAT procedure
10 | Text Box | 7 | Hasan Asad | Shall be from AVL
11 | Text Box | 8 | Mahdi Ali | Correct EPC equipment tags to be used.
| Cloud | 8 | Mahdi Ali
12 | Callout | 9 | balagangadhar.k | 094FA9401
| Arrow | 9 | Nalini Mohan
13 | Text Box | 9 | Mahdi Ali | Correct EPC equipment tags to be used.
| Arrow | 9 | Mahdi Ali
| Arrow | 9 | Mahdi Ali
| Cloud | 9 | Mahdi Ali
14 | Callout | 9 | Nalini Mohan | subject to Prequalification Exercise and COMPANY's approval
15 | Callout | 9 | BD Mori | Duty specification (094-S-DAT-00002-001) and
16 | Text Box | 11 | Hasan Asad | Belts shall be antistatic type.
17 | Text Box | 14 | Hasan Asad | All scrapers shall be accessible
18 | Text Box | 15 | Hasan Asad | Access for belt replacement with vulcanising machine shall be considered during design.
19 | Text Box | 15 | Hasan Asad | System for sulphur smoke detection shall be provided.
20 | Text Box | 15 | Nalini Mohan | Provide deluge system for conveyors as per bid clarification T1759
| Arrow | 18 | Hasan Asad
21 | Text Box | 18 | Hasan Asad | Flexible coupling is simpler and easier to maintain.
| Cloud | 18 | Hasan Asad
22 | Text Box | 25 | Hasan Asad | Supplier for Auto. lubrication system shall be AVL, new suppliers shall be pre-qualified.
| Line | 28 | Ebrahim
| Arrow | 28 | Ebrahim
23 | Text Box | 28 | Ebrahim | LED type lamps shall be used. Refer to BMPS-P1, clause 8.2
| Line | 28 | Ebrahim
| Line | 28 | Ebrahim
24 | Text Box | 28 | Ebrahim | Shall be as per BMPS-P1, clause 8.2, f.
25 | Call-out | 28 | Ebrahim | type 316L (powder coated stainless steel is preferable) or Die cast aluminium.
26 | Call-out | 29 | Ebrahim | and 230V as per BMPS-P1 clause 6.16, c
| Ellipse | 29 | Ebrahim
27 | Text Box | 36 | Hasan Asad | Design of max. bag weight shall be provided and how to replace the bag and dispose/transfer to the ground level.
28 | Text Box | 36 | Hasan Asad | Add: Conveyor
29 | Text Box | 37 | Hasan Asad | Cleaning facility/window with discharge ports and access to be provided for solid sulphur removal.
30 | Text Box | 44 | Nalini Mohan | The environmental concerns related to this design package shall be called in requisition and Contractor is advised that conveyors shall be configured to mitigate the HSE impact due to fugitive dust. It needs to be minimized the generation of static charge and product dusting at the transfer point, hoods, static conducting belts, etc.
31 | Text Box | 44 | Hasan Asad | Shall be covered with antistatic rubber to eliminate source of sparks - This is implemented in Bapco SHF after fire incident.
32 | Text Box | 44 | Hasan Asad | The sliding valve shall be designed to eliminate the build-up of sulphur around the valve seat to avoid seizure and jamming problem - It is also recommended to provide with manual facility to assist with any malfunctioning operation (jamming).
33 | Text Box | 50 | Nalini Mohan | Particular Technical Specification shows the requirement of guarantees referenced by Particular Terms & Condition of PTC-601. Contractor to confirm if this document is attached in this requisition.
34 | Text Box | 50 | Hasan Asad | The production line from the Collecting Conveyor to the stockpile shall be in continuous operation, hence, spare motor & gearbox assembly shall be considered for the critical conveyors.