## 000-S-ITP-70003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Add Unit name '2HCU"
2 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
3 | Text Box | 2 | Mahdi Ali | FEED document number shall not be used.
4 | Callout | 2 | Yousif Ahmadi | Add: Pre-shipping inspection section
5 | Callout | 2 | Yousif Ahmadi | Add: Electrical, Instruments cables and JB in page 6
6 | Cloud+ | 2 | Yousif Ahmadi | Inspection level are set as 4 to be change to 3 in pages 3 to 7
7 | Text Box | 3 | Ahmed Bucheeri | WPS & PQR for reviewing
8 | Text Box | 4 | Ahmed Bucheeri | WPS & PQR for reviewing
9 | Text Box | 6 | Ahmed Marhoon | Inspection and Test Plan to include the participation of the client in accordance with the BMP agreed procedures. Loop testing, if any, plan to be detailed. Tests related to instrumentation, control and safety to comply with the BMPS J series specifications/instructions. As a minimum, the relevant Checklist as agreed for the BMP shall be referenced in the ITP.
10 | Text Box | 7 | Ahmed Bucheeri | WPS & PQR for reviewing