## 000-S-ITP-80008-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Jeung.Kim | The Criticality rating and its Inspection level shall be verified before placing purchase order.
2 | Callout | 2 | Saeed Taher | Add c for contractor for all pages
3 | Callout | 2 | Saeed Taher | Add o for owner for all pages
4 | Callout | 2 | Saeed Taher | Owner Inspection requirements to be finalized during ITP finalization with vendor
5 | Callout | 3 | Saeed Taher | Add WPS & PQR for all welded equipment - BMPS-B1
6 | Text Box | 3 | Hasan Asad | Spare rotor shall undergo test run.
7 | Text Box | 3 | Hasan Asad | W
8 | Callout | 3 | Dowon Pyun | Integrally Geared Compressor
9 | Callout | 5 | Saeed Taher | Expander
10 | Callout | 7 | Dowon Pyun | Cooling type is not yet fixed, ITP for air cooled H/E is required.
11 | Text Box | 11 | Hasan Asad | MCM System test
12 | Call-out | 13 | Ali Abbas | instrumentation and systems inspections, FAT,I-FAT, SAT and function checks, refer to BMPS J series specifications