## 000-S-MRQ-80008-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Saeed Taher | Mechanical data sheets to be provided for individual equipment
2 | Text Box | 1 | Jeung.Kim | Typical Comment: All design data including data sheet have to be detail design developed and such developed and approved design has to be implemented in the purchase order.
3 | Callout | 2 | Julio.Aguilar | Add: BMPS-A8
4 | Text Box | 2 | Dowon Pyun | Add following specifications; Environmental Philosophy, BMPS-A14 Piping Fabrication, Installation and Testing, BMPS-B3 Shop Inspection Requirements, FATs and SATs, BMPS-B11
5 | Text Box | 2 | Dowon Pyun | Add Air Cooled Heat Exchangers, BMPS-E7"
6 | Text Box | 2 | Dowon Pyun | Process Design Basis shall be attached
7 | Text Box | 2 | Nalini Mohan | Provide Plot Plan, Hazardous Area Classification, Nitrogen System Block Flow Diagram as part of initial submission
8 | Text Box | 3 | Dowon Pyun | Add Instrument Piping Classes, BMPS-J5
9 | Text Box | 3 | Dowon Pyun | Add Machine Condition Monitoring (MCM) System, BMPS-J15
10 | Text Box | 3 | Dowon Pyun | Add Safety Integrity Level (SIL) Determination Procedure, BMPS-J29
11 | Callout | 3 | Dowon Pyun | All project specifications counter called in this specification should be informed before of placing order to Vendor
12 | Callout | 3 | Dowon Pyun | All project specifications counter called in this specification should be informed before of placing order to Vendor
13 | Text Box | 3 | Dowon Pyun | Add job specification for material preservation at site, 2520-Z000-MS-6740-52
14 | Text Box | 3 | Nalini Mohan | Add BMPS-L1, L3, L9, L11, L12, L13, L14, L16
15 | Callout | 6 | Nalini Mohan | Include Asset Information Sheets for all applicable equipment