## 000-S-MST-60004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 4 | scott.hillman | Verify only excel spreadsheet is required OR survey drawings in global and local systems are also required.
2 | Text Box | 4 | scott.hillman | Define Local and Global system Viz (WGS84 OR UTM Zone 39N coordinates Ain Al ABD Datum OR Refinery Grid.
3 | Callout | 6 | scott.hillman | Use of the word "Practice is ambiguous. Delete and replace with "Technical Specification"
4 | Callout | 6 | scott.hillman | "and licensed to perform"
5 | Callout | 6 | scott.hillman | "services"
6 | Callout | 7 | scott.hillman | Bapco HSE Management Plant and Project HSE plan to be included in references
7 | Callout | 8 | scott.hillman | General Note - Delete "Owner"
8 | Callout | 9 | scott.hillman | Define Local and Global system Viz (WGS84 OR UTM Zone 39N coordinates Ain Al ABD Datum OR Refinery Grid.
9 | Text Box | 11 | scott.hillman | Bapco approved subcontractors proposed to be used for excavation and concreting related works (survey monument construction)
10 | Callout | 12 | scott.hillman | All surevying personnel to qualify Bapco trade testing requirement. Survey equipment and vehicles shall be presented to Bapco for testing and tagging.
11 | Callout | 13 | scott.hillman | Bapco approved contractors shall be engaged for excavation and monument construction works
12 | Callout | 16 | scott.hillman | and ASCI files wherever applicable
13 | Text Box | 19 | scott.hillman | Risk Assessment and Method Statement to be submitted, defining in detail the methods and management practices to be used to ensure the work is executed in a safe, timely and efficient manner, with due regard to the requirements of the contract. - Subco
14 | Callout | 24 | scott.hillman | What about clouded area topographic Survey?