## 005-A-BOD-00001-001-RA-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the correct document format which was sent to the Project Mail Box on 9th Apr 2018, included in ATTACHMENTS TO 000-A-PRO-50006-0001_A.zip
2 | Call-out | 1 | Edgardo | Please provide space between C4 and Storage
3 | Call-out | 1 | Abdul Rahim | Pressurised
4 | Callout | 1 | BD Mori | This BOD shall be revised in entirety including pumping and storage capacity after completion of SGP FEED
5 | Call-out | 1 | Abdul Rahim | Pressurised LPG
6 | Call-out | 1 | Abdul Rahim | Storage capacities should not be reduced
7 | Cloud+ | 3 | Sameer.Ahmed | Statement to be deleted.
8 | Callout | 3 | Bernard.Grace | List out the factors that affect the design. Safety distances, storage requirements, fire fighting, etc
9 | Call-out | 4 | MAK | Remove any letter in front of the Unit No. e.g. the Unit No. shall read 050, 005, 056, 06, 907, etc.
10 | Callout | 5 | Bernard.Grace | To what extent?
11 | Cloud+ | 5 | Sameer.Ahmed | Delete the statement
12 | Callout | 5 | Bernard.Grace | What about firefighting, delivery philosophy of bottles to cages etc?
13 | Call-out | 5 | Edgardo | These values need to be confirmed based on the final design of the SGPs
14 | Callout | 5 | Bernard.Grace | Why is this proposed, list the design factors that influenced this decision
15 | Call-out | 5 | Mahdi Ali | Use correct format for equipment numbers
16 | Callout | 6 | BD Mori | Bapco LPG product specification for H2S is "Negative" per ASTM D 2420 test method and Corrosion, Copper Strip per ASTM D 1838 test is 1 Max. LPG product specification can not be met with 5 wppm H2S content in Propane.
17 | Callout | 6 | BD Mori | Bapco LPG product specification for H2S is "Negative" per ASTM D 2420 test method and Corrosion, Copper Strip per ASTM D 1838 test is 1 Max. LPG product specification can not be met with 5 wppm H2S content in Propane.
18 | Call-out | 7 | Abdul Rahim | bullets
19 | Call-out | 7 | Abdul Rahim | bullets
20 | Call-out | 7 | Edgardo | at
21 | Callout | 7 | Bernard.Grace | including empty bottles
22 | Callout | 7 | BD Mori | If the bullet is contaminated with high H2S in the C3 or C4 stream, it is difficult to decontaminate the bullet/s. Handling of off spec C3/C4 on high H2S content shall explained and included in this document.
23 | Callout | 7 | Salman Jaffer | to
24 | Callout | 8 | Dowon Pyun | To be noted depressurization temperatures
25 | Callout | 8 | Salman Jaffer | 1&2SGPs
26 | Cloud+ | 8 | Sameer.Ahmed | change to "Units"
27 | Callout | 8 | BD Mori | Refer section 4.1. Provide note : Maximum operating temperature is 135°F considering cooling water failure in C3/C4 trim cooler in 1/2SGP
28 | Call-out | 8 | Edgardo | Please change to "C3 / C4 Refrigerated Storage Facilities at Wharf (Unit 051)"
29 | Call-out | 8 | MAK | These tag numbers might be changed to EPC new tag numbers which will be sent officially to JV.
30 | Callout | 8 | Salman Jaffer | Modify to: • Two C3 Transfer pumps for LPG blending (70% C4, 30% C3) to existing Horton Spheres and local facilities; • Two C3 Export pumps for C3 export to Refrigerated Storage facilities at Wharf; • Two C4 Transfer pumps for LPG blending (70% C4, 30% C3) to existing Horton Spheres and local facilities; • Two C4 Export pumps for C4 export to Refrigerated Storage facilities at Wharf; • Two C4 Injection pumps for injection into Gasoline/Naphtha lines; • Two OFFSPEC LPG pumps for Reprocessing.
31 | Callout | 9 | BD Mori | Recheck. This value should be 635 BPH. Normal production rate is 7.4 MBPD/14hr*(1.2)= 635 BPH
32 | Text Box | 9 | Edgardo | C3 / C4; For consistency with the rest of the paragraph, the phrase "Propane / Butane Transfer pumps" can also be used
33 | Call-out | 9 | Edgardo | insert "C3 / C4"
34 | Callout | 9 | BD Mori | Recheck. This value should be 1012 BPH. Normal production rate is 11.8 MBPD/14hr*(1.2)= 1012 BPH
35 | Call-out | 9 | Abdul Rahim | Horton spheres
36 | Call-out | 9 | Edgardo | change to "C3 / C4"
37 | Callout | 10 | Salman Jaffer | 1&2SGPs
38 | Callout | 10 | BD Mori | Normal C3+C4 production is 7.4 MBPD+11.8 MBPD for two SGP trains. At 50% turn down operation of one SGP train the production is 4.8 MBPD. The basis for 6274 BPD is not clear.
39 | Call-out | 10 | Abdul Rahim | C4
40 | Call-out | 10 | Abdul Rahim | C4
41 | Call-out | 10 | Abdul Rahim | at Refinery Tank Farm
42 | Call-out | 11 | MAK | These tag numbers shall be changed to EPC new tag numbers which will be sent officially to JV.