## 005-A-PFD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Abdul Rahim | add line number
2 | Callout | 1 | BD Mori | As per P&ID, indicate this valve as XV
3 | Call-out | 1 | Edgardo | Please add V5005
4 | Call-out | 1 | Edgardo | Rewrite Unit 051 without the prefix "f"
5 | Cloud+ | 1 | Sameer.Ahmed | Show full tag number i.e. 005V5006/005V5005
6 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. PFD shall be modified to incorporate the updated streams data and H&M balance.
7 | Callout | 1 | BD Mori | This stream data shall be under hold till completion of 1/2 SGP design.
8 | Callout | 1 | BD Mori | This valve symbol is overlapping with the next line. Improve drafting.
9 | Callout | 1 | BD Mori | What is the basis for revising this pressure? FEED PFD, this value is 130 psig. Is existing sphere operating pressure considered? Keep on hold.
10 | Callout | 1 | BD Mori | What is the basis for revising this pressure? FEED PFD, this value is 72 psi. Shall be on hold until existing sphere pressure is known.