## 005-A-PFD-00001-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | BD Mori | As per P&ID, indicate this valve as XV
2 | Call-out | 1 | Edgardo | Please add P5044A/B
3 | Cloud+ | 1 | Sameer.Ahmed | Show full tag number i.e. 005V5006/005V5005
4 | Call-out | 1 | Ali Abbas | show signal line break
5 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. PFD shall be modified to incorporate the updated streams data and H&M balance.
6 | Callout | 1 | BD Mori | This valve symbol is overlapping with the next line. Improve drafting.