## 010-A-PFD-00001-004-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Refer to the first sheet for the General Comments.
2 | Text Box | 1 | Ahmed Ali | E0016
3 | Text Box | 1 | Ahmed Ali | E0017A/B
4 | Text Box | 1 | Ahmed Ali | V0009
5 | Text Box | 1 | Ahmed Ali | V0010
6 | Callout | 1 | Mohamed Ayyash | add equipment number (apply to all streams on all sheets)
7 | Text Box | 1 | Ahmed Ali | E0018A/B
8 | Text Box | 1 | Ahmed Ali | V0011A/B
9 | Text Box | 1 | alexis.martinez | GENERAL: Equipment TAG number shall be modified based on the list and PFDs Mark-up sent to Contractor.
10 | Text Box | 1 | alexis.martinez | GENERAL: All the utility stream and the correspondent Heat and Material Balance stream number shall be shown on a separate Utility Flow Diagram (UFD).
11 | Call-out | 1 | 986131 | Depict the compressor, KOD and the associated equipments in a straight line for clarity. Show the A and B compressors separately. similar to the 2HCU make up hydrogen compressor representation in the PFD.
12 | Text Box | 1 | alexis.martinez | GENERAL: locate the pumps and compressor data blocks aligned with the corresponding equipment.
13 | Text Box | 1 | alexis.martinez | GENERAL COMMENT APPLICABLE TO ALL PFD'S: - As required in BMPS A8, 7.2.7 item 4 add the note stating: The data on equipment data blocks indicate the normal operating case for the unit and may not be the design case. - All tag numbers shown close to or inside the equipment to have the full equipment number including the unit number - this is based on the updated BMPS-A8 (issued on 09 April 2018)
14 | Callout | 1 | alexis.martinez | Capacity and suction/discharge operating pressures for first and second stage of compressor 010K0001A/B, are not matching with operating condition on FEED datasheet
15 | Callout | 1 | alexis.martinez | Correct duty of atmospheric column overhead trim cooler: as per H&MB the value is 9.2 MMBtu/hr.
16 | Callout | 1 | alexis.martinez | Correct duty of Compressor Interstage Cooler: as per H&MB the value is 1.6 MMBtu/hr.
17 | Call-out | 1 | Ahmed Marhoon | Contractor to critically review the current Spill Back arrangement with regard to the control configuration. Currently, two selector switches are provided for the operator to change the switch between the suction of 1st stage Compressors A & B and another one to switch between the discharges of 2nd stage Compressors A & B. This configuration may lead to misalignment of pressure controllers/spill back system if done manually. Contractor to provide adequate measures to meet equipment safety and process availability requirements taking into consideration the Hazop3 recommendation and in consultation with the Compressor Vendor.