## 010-C-GAD-10002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 2
2 | Call-out | 2 | MAK | 2
3 | Call-out | 3 | MAK | 2
4 | Call-out | 2 | MAK | 2
5 | Text Box | 1 | MAK | 3
6 | Call-out | 3 | MAK | 3
7 | Text Box | 1 | MAK | 010 - 7CDU
8 | Text Box | 2 | MAK | 010 - 7CDU
9 | Text Box | 3 | MAK | 010 - 7CDU
10 | Cloud+ | 1 | Adnan Alothman | Add negative "-" to the Ext. Design Pressure values.
11 | Cloud+ | 3 | 986131 | Arrangement shown is not adequate to ensure proper reboiled operation please rectify.
12 | Callout | 2 | Yousif Ahmadi | CA for removable of 12 Cr is 0 mm in Data sheet. Check and confirm.
13 | Cloud+ | 3 | 986131 | Consider moving the manway on the other side for better access. accordingly move the M2.
14 | Call-out | 3 | 986131 | Correct equipment number
15 | Call-out | 3 | 986131 | Correct equipment number
16 | Call-out | 3 | 986131 | Height of the baffle to be provided.
17 | Call-out | 3 | 986131 | How to ensure steam out on this side of the baffle?
18 | Cloud+ | 2 | 986131 | In note 21 correct equipment number
19 | Callout | 2 | alexis.martinez | In Page 2, Note 19, add the column pressure drop and the liquid static head used to calculate the design pressure at Bottom Tangent Line (B.T.L.)
20 | Call-out | 3 | alexis.martinez | In Page 3, the nozzles N9A and N11A shall be at the same elevation.
21 | Call-out | 3 | alexis.martinez | In Page 3, the nozzles N9B and N11B shall be at the same elevation.
22 | Call-out | 3 | alexis.martinez | In Page 3, to be consistent with column 010C0001, the Manway nozzles shall be numbered from bottom to top.
23 | Cloud+ | 1 | Yousif Ahmadi | Interm. Skirt Effeciancy is 0.85 and CA is 3 mm per FEED data sheet. Check and confirm
24 | Call-out | 1 | 986131 | item 1 & 3 to be distinguished as top head and bottom head. based on note 19 it appears that the selected design pressure is not adequate. please correct as nessary.
25 | Callout | 1 | Adnan Alothman | N8 is 24 inch as per FEED drawing. Check and confirm
26 | Callout | 2 | alexis.martinez | On page 2, delete the note 29.
27 | Callout | 1 | Adnan Alothman | Operation Press. of Top section is 18 per FEED drawing. Check and confirm.
28 | Call-out | 2 | 986131 | Please check the applicability and provide clear guide line.
29 | Call-out | 3 | 986131 | provide detail drawing with support arrangement.
30 | Call-out | 3 | 986131 | Provide details of the stripping steam inlet pipe.
31 | Text Box | 3 | alexis.martinez | Provided the details of nozzle N11 with the Vortex Breaker
32 | Call-out | 3 | alexis.martinez | Provided the details of nozzle N6 with the Vortex Breaker
33 | Call-out | 1 | 986131 | Repeat the Name plate on each page.
34 | Callout | 1 | Adnan Alothman | Requirement of Fire Proofing to be checked and confirm.
35 | Call-out | 3 | 986131 | Show the bottom baffle.
36 | Text Box | 1 | MAK | Use the latest A3 Border
37 | Text Box | 2 | MAK | Use the latest A3 Border
38 | Text Box | 3 | MAK | Use the latest A3 Border