## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | alexis.martinez | Include the conical section as part of the top section. As per Data Sheet Note 5. "TOP SECTION (INCLUDING CONICAL SECTION):" | Conical section is included in top section as shown in the last page | N
2 | Callout |  | alexis.martinez | The equipment TAG number and the description shall be shown in all the sheets. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N
3 | Call-out |  | 986131 | Tag number of the equipment would change and needs to be update based on revised tag numbering. | Noted. It will be implemented in revision A | Y
4 | Call-out |  | 986131 | Repeat the clouded section on all the pages. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N
5 | Callout |  | alexis.martinez | Change the note 22 "The design temperature can be raised to 500°F unless the resulting combination of design pressure and temperature exceeds the ANSI B16.5 flange rating" as per BMPS-A3. | Noted. It will be implemented in revision A | Y
6 | Callout |  | alexis.martinez | Add the note "Column will be subjected to steam-out operation. Additional design conditions shall be -10 psig at 300 °F" | Already included in the first page | N
7 | Call-out |  | Ahmed Marhoon | Note 23 needs to be reworded to be addressed to the manufacturer. Instrumentation nozzles details will be finalized at a later stage of the detail design and confirmed post Hazop3/SIL studies. Refer to Typical comment on sheet 1 of 019-C-GAD-10010-001-RAP. | Noted. It will be implemented in revision A | Y
8 | Call-out |  | 986131 | Consider relocating the manway on the other side of baffle for better accessibility. And accordingly M4 location to be checked. | This is a sketch. Manhole and baffle position will be fixed in a later stage | N
9 | Call-out |  | 986131 | Arrangement shown to be reviewed and modified based on the re-boiler configuration (i.e. once through or circulating). Current arrangement shown is prone to liquid entrainment and foaming. Review during detail engineering. | Reboiler configuration is once through. Refer to bottom arrangement details on Process data sheet 010-C-DAT-10004-001. | Y
10 | Call-out |  | 986131 | Update P&ID representation accordingly. | Agreed. P&ID will be updated accordingly. | Y