## 010-E-DAT-00004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ahmed Ali | General note for all the equipment downstream of the desalter "in future there will be caustic soda injection facility in the outlet of the desalter, all equipment downstream to be design for x ppm of caustic
2 | Call-out | 1 | 986131 | Refer the previous comment on this page, x = 2 PTB.
3 | Call-out | 1 | Mahdi Ali | Remove space
4 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all document
5 | Callout | 1 | Mohamed Ayyash | 7CDU ( apply to all sheets)
6 | Callout | 2 | alexis.martinez | There is an inconsistency with the information on FEED plot plan BRA-229571, Sheet 1 and 2, they are shown as stack on the same platform. This has to be reviewed and correct the documents accordingly.
7 | Callout | 2 | Mohamed Ayyash | Enlarge font (Too small) for all pages
8 | Call-out | 2 | 986131 | Page 2, Row 30: As per PFD pressure is 100 psig. please review and correct PFD or Data sheet as required.
9 | Call-out | 2 | 986131 | As per description of page 2, row 13 liquid (excluding water) to be filled, how ever the total flow is quoted, please correct
10 | Call-out | 2 | 986131 | page 2, row 15: Fill the water flow in the stream
11 | Cloud+ | 3 | 986131 | Add note 16 here.
12 | Cloud+ | 3 | 986131 | move note 16 from here and add near tube side pressure
13 | Callout | 3 | alexis.martinez | Design pressure on shell and tube is bigger that FEED design pressure. The reasons to this increment in design pressure need to be sent to the owner.
14 | Cloud+ | 3 | Yousif Ahmadi | Code must be latest: 2017
15 | Call-out | 3 | 986131 | General comment: while selecting between options, use a circle or tick mark. by making it black it creates a confusion if "yes" is struck off.
16 | Text Box | 4 | Hasan Asad | Vendor to consider complete unit removal for shop overhaul.
17 | Call-out | 5 | 986131 | It is not clear what is specified flow mean - is it the design flow or normal flow. Please correct as nessary
18 | Callout | 5 | alexis.martinez | Add what the document MOC-PRO-GEN-020 stand for in note 10.
19 | Cloud+ | 5 | Yousif Ahmadi | Tube to baffle hole clearance is not as per FEED drawinbg
20 | Callout | 6 | alexis.martinez | Equipment Numbers need to be updated as per the new numbering provided by owner.
21 | Text Box | 6 | Hasan Asad | LCCA to be provided for 20 years.