## 010-K-DAT-00001-001-RAP-CS.XLSX
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mahdi Ali | remove space
2 | Call-out | 1 | Mahdi Ali | Remove p
3 | Call-out | 2 | Tapas | Please recheck the figures based on the unit of flow selected and correct as necessary.
4 | Call-out | 2 | Tapas | Contractor to fill in the missing data - compressibility factor, Cp/Cv etc. as this are already available with the contractor. The Vendor recalculation would serve as a double check for these critical parameters.
5 | Callout | 2 | alexis.martinez | The compressor suction pressure shown is a vacuum pressure (it does not match with FEED pressure). The compressor can be designed to operates in vacuum but this the normal operating pressure.
6 | Callout | 2 | alexis.martinez | Normal operating case for H&MB Design and alternate case have to be included.
7 | Call-out | 2 | Tapas | Contractor to fill the data.
8 | Callout | 2 | Mohamed Ayyash | No. (Typo) apply to all document
9 | Call-out | 2 | Ahmed Ali | confirm the figures look to high
10 | Callout | 2 | alexis.martinez | Confirm the molecular weight of CDU OVHD vapour (53.83 lb/lb-mol) at the compressor inlet conditions (109°F and 13.7psia)
11 | Call-out | 2 | Tapas | The suction pressure indicated in vacuum,which is different from FEED. A vacuum in the compressor suction is prone of air leakage and is potentially dangerous and unwarranted. The FEED configuration the Pressure drop in the compressor KOD and associated pipes is about 0.7 psi. Contractor to size the KOD and piping such that the pressure drop is within the FEED specified value.
12 | Call-out | 3 | Tapas | Please fill in the molecular weigh (MW) for the pseudo components. In case the MW weight is different for the various case. Show them below the composition in bracket and a note explaining that they indicate MW.
13 | Cloud+ | 3 | Yousif Ahmadi | Per FEED: TROPICAL, MARINE, SALT, SAND, HIGH AMBIENT TEMPERATURE
14 | Call-out | 3 | Tapas | Crude unit overhead contains Chloride (as HCI or ammonium chloride) and we can expect minor quantity of chloride in the gas going to the compressors. API 618 specifies that "IF CHLORIDES ARE PRESENT, EVEN MINUTE TRACES, IN THE GAS BEING COMPRESSED, IT MUST BE INCLUDED" Therefore, Contractor to specify the expected chloride considering all operating scenarios.
15 | Callout | 4 | Mohamed Ayyash | Move to center of cell. (both 1st stage and 2nd stage)
16 | Text Box | 5 | Hasan Asad | Shall be SS material.
17 | Callout | 6 | Mohamed Ayyash | write 54 on the 2nd line to ovoid overlaping with the line
18 | Text Box | 6 | Hasan Asad | Required
19 | Callout | 8 | Mohamed Ayyash | Align
20 | Text Box | 9 | Hasan Asad | Valve spec's will be reviewed once available.
21 | Callout | 9 | Mohamed Ayyash | rewrite ( overlapping with slashes (/)
22 | Text Box | 9 | Hasan Asad | Verify PTFE piston and rider rings.
23 | Callout | 9 | Yousif Ahmadi | <31 HRC note to be written against Piston Rods Hardness
24 | Callout | 9 | Mohamed Ayyash | Align
25 | Callout | 9 | Yousif Ahmadi | add "as per BMPS-K1) point 6.10.4.1 to PISTON RODS(S): MATERIAL/YIELD, PSI
26 | Text Box | 10 | Hasan Asad | To be advised by Vendor
27 | Call-out | 14 | Ahmed Ali | 48F as per BMPS-A1
28 | Text Box | 15 | Hasan Asad | Pulsation Suppression shall be equipped with KO drum and pot connected to flare. The process shall be automated - requirement basis Owner existing Refinery experience.
29 | Callout | 17 | Mohamed Ayyash | Delete
30 | Callout | 18 | Mohamed Ayyash | Remove block
31 | Callout | 20 | Isamu | Delete as it has no room here
32 | Callout | 20 | Mohamed Ayyash | Remove block
33 | Call-out | 21 | Tapas | Refer to note 1 margins: Based on H&MB from FEED the margins work out to 60% and 45% for 1st and 2nd stage respectively. Contractor to review and correct as necessary.
34 | Callout | 21 | Mohamed Ayyash | Align
35 | Cloud+ | 21 | Tapas | Refer to Note 13 - This appears to be based on a Technical clarification which is not based on the stipulated project procedures, not recorded in the project documents and Owner is not informed. Therefore, the Technical clarification is invalid. Contractor to ignore any details that they may receive on the clarification and proceed on the FEED design basis.
36 | Callout | 21 | Mohamed Ayyash | Complete line
37 | Callout | 21 | Mohamed Ayyash | Align
38 | Callout | 21 | Mohamed Ayyash | Delete line
39 | Call-out | 21 | Raj | Ignore the comment regarding check valve
40 | Call-out | 21 | Ahmed Marhoon | In addition to manual operation, automatic unloading system to be considered with the necessary instrumentation (including smart positioners with FF capability).
41 | Callout | 21 | Mohamed Ayyash | Duplicate figure of 2. Re number. This applies to pages 21, 22& 23
42 | Call-out | 21 | Tapas | A simple arithmetic calculation (without considering the effect of component partial pressure based on the recycle components) considering 5 steps indicate a that the recycle required is 12%. Contractor to recheck the number. Ignore the comment if the number is based on a rigorous calculation done using a process simulator.
43 | Cloud+ | 21 | Yousif Ahmadi | Correct the equipment numbers
44 | Callout | 21 | Mohamed Ayyash | Delete line
45 | Callout | 21 | alexis.martinez | The use of check valve in the vents to flare is not a common practice. Evaluate the requirement of check valve on the vents lines.
46 | Text Box | 21 | Mahdi Ali | Use Bapco number
47 | Callout | 21 | Mohamed Ayyash | Delete lines
48 | Call-out | 21 | Ahmed Marhoon | The understanding is that remote will be done in DCS. The relevant PID to be updated accordingly.
49 | Call-out | 21 | Tapas | Note 14 is not clear. Please clarify who would update the gas composition. If the composition is on HOLD by the contractor. Then please indicate so.
50 | Callout | 22 | Mohamed Ayyash | Delete lines
51 | Callout | 22 | Mohamed Ayyash | Delete lines
52 | Callout | 23 | Yousif Ahmadi | Typo error: Licensor, confirm the drawing number
53 | Callout | 23 | Yousif Ahmadi | Note 56: ASME VIII, Div 1 or VIII Div 1 d??
54 | Text Box | 23 | Hasan Asad | Drain KO Drum shall be provided with manual/automatic draining facility.
55 | Text Box | 23 | Ahmed Marhoon | The following are comments related to instrumentation and control: 1. In addition to BMPS-J1, J2 & J6, all applicable BMPS-J series to be referenced (such as J3, J31 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Spill back arrangement/design shall be reviewed and confirmed by the supplier. 6. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 7. Requirement of MCM to be detailed with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 8. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 9. All the machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 10. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 11. Assistance and involvement of the vendor during CHAZOP/Hazop workshops/studies to be considered. 12. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 13. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 14. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 15.Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.
56 | Call-out | 23 | Ahmed Marhoon | All applicable BMPS-J series to be added.
57 | Callout | 23 | Mohamed Ayyash | Complete missing sections of table line in all pages
58 | Text Box | 24 | Sankara | Delete Ex-p
59 | Callout | 24 | Mohamed Ayyash | Add space
60 | Callout | 24 | Mohamed Ayyash | Add space
61 | Callout | 24 | Mohamed Ayyash | move the number to center of cell
62 | Text Box | 24 | Mahdi Ali | Remove p from unit number
63 | Cloud+ | 24 | Yousif Ahmadi | The number to be changed 010K0001A/B
64 | Text Box | 25 | Ahmed Ali | Compressor casing shall be provided with N2 connection to purge the casing in case of shutdown